## Updates of Ecosense
Sr.no | Date | Page
1 | 2024-08-17 | Designed bhurja page
Sunday
2 | 2024-08-19 | Designed bhurja more Details page
3 | 2024-08-20 | Designed jyot page
4 | 2024-08-21 | Designed jyot more details page
5 | 2024-08-22 | Updates on website as per suggestions
6 | 2024-08-23 | FAQ dropdown changes on website
7 | 2024-08-24 | Website Updated for respnsive on mobile
Sunday
8 | 2024-08-26 | FAQ dropdown changes on website in singledropdown all questions and answers
9 | 2024-08-27 | updates on scrolling images added one image and changed style
10 | 2024-08-28 | Updated videos for jyot and bhurja for responsive on website
11 | 2024-08-29 | Designed neerdhur page
12 | 2024-08-30 | Designed neerdhur more details page
13 | 2024-08-31 | Designed Ecochulla Oval page
14 | 2024-09-09 | Footprint image added to Products
15 | 2024-10-22 | Mail receved for website correction. Correction understood
Corrections For Website
16 | 2024-10-23 | correction started for website. 1.Oval dos and donts are corrected 2.Eleggant efficiency is corrected 3.Bhurja FAQ dropdown is corrected
17 | 2024-10-24 | 1.Jyot 2.5 product new img added. 2. Eco cooker product new img added and Eco Cooker page img added. 3. In about us teams photo updated. 4. Blogs design changed more responsive and blog card style is changed
18 | 2024-10-25 | All corrections are deployed.
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34