## Sheet1
Work Timeline
|  |  | 2024-09-29 | 2024-09-30 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-05 | 2024-10-06 | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-10 | 2024-10-11 | 2024-10-12 | 2024-10-13 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-10-18 | 2024-10-31 | 2024-11-04 | 2024-11-06 | 2024-11-08
| Activity | Responsibility
Task 1 | Finalise Data Structure
1 | Create Data Structure | bar: 2024-09-29
2 | Confirmation of Data Structure | bar: 2024-09-29; 2024-10-02
Task 2 | Create Database
1 | Create Database , Tables Stored Procedure Function if required | bar: 2024-10-03
Task 3 | Design of UI
1 | Design Dashboard | bar: 2024-09-29 to 2024-10-07; 2024-10-09 to 2024-10-11
2 | Add Document form | bar: 2024-10-05 to 2024-10-07; 2024-10-09
3 | View Documents | bar: 2024-10-09 to 2024-10-11
4 | Edit Document | bar: 2024-10-10 to 2024-10-13
5 | Navigation bar toggling | [15 empty] | 8h | bar: 2024-10-10 to 2024-10-11
6 | Website Hosting on iis | [16 empty] | 8h | bar: 2024-10-10 to 2024-10-11
7 | theam toggling | [17 empty] | 8h | 8h | 8h | bar: 2024-10-10 to 2024-10-11
8 | View old Document option | [19 empty] | 8h | bar: 2024-10-12 to 2024-10-13
9 | View profile page | [20 empty] | 2 days | bar: 2024-10-07; 2024-10-09
10 | In navigation bar report page | [21 empty] | 2 days | bar: 2024-10-10 to 2024-10-11
11 | Change note | bar: 2024-10-10 to 2024-10-11
12 | Login options according to user roll | [22 empty] | 8h | bar: 2024-10-12 to 2024-10-13
Task 4 | Binding of Application with database
1 | bar: 2024-09-29; 2024-10-02 to 2024-10-07; 2024-10-09 to 2024-10-11
2 | bar: 2024-10-12 to 2024-10-13
3 | bar: 2024-10-12 to 2024-10-13
Task 5 | Testing
1 | bar: 2024-10-12 to 2024-10-13
2
3
4
5
6
* Implementation time is subject to Confirmation from directors and rework
As we don't have have mobile app developer we may reuire more time for mobile App by estimated time
| 8H | 8 hours
| 16H | 16 hours(8Hrs per head)
Working
Sunday
Holiday
Spend Time with Abhijeet(new joinee) To give training & explain about project

## Sheet3 (hidden)
Work Flow For Process Parameter Project
Sr.No | Task | Implementation Time | Tentative Date | Required Manpower | Remark
1 | Create Data Structure | 2 days | 2019-07-23 | 1
2 | Confirmation of Data Structure from sandeep sir | 2 days | 2019-07-25 | 1
3 | Create Web Application for Master Entry | 2 week | 2019-08-06 | 1
4 | Design UI for supervisor App(android app for tab) on paper | 2-3 days | 2019-08-08 | 2
5 | Approval of design from directors | 2 days | 2019-08-10
6 | Design UI for supervisor App(android app for tab) | 2 week | 2019-08-26 | 2
4 | Design UI for Auditor App(android app for tab) on paper | 2-3 days | 2019-08-30 | 2
5 | Approval of design from directors | 2 days | 2019-09-02
6 | Design UI for Auditor App(android app for tab) | 2 week | 2019-09-17 | 2
7 | Binding of App with database | 2 week | 2019-09-30 | 2
8 | Testing of Web application | 1 week |  |  | Testing will done simultaniously after completion of application
9 | Testing of Supervisor App | 1 week |  |  | Testing will done simultaniously after completion of application
10 | Testing of Auditor App | 1 week |  |  | Testing will done simultaniously after completion of application
* Implementation time is subject to Confirmation from directors and rework