## Rev 09 (2)
STPPL | Standard Operating Procedure |  | Purpose : To standardise the process of Initial Production Control (IPC) / Initial Flow Management (IFM). |  |  |  | STPPL/MKD/SOP/16
| Title : Initial Production Control (IPC) / Initial Flow Management (IFM) |  | Scope : For new product development and control. For ECN approved by customer For PCN etc. and For high volume increased. |  |  |  | Rev. No.: 09
Rev date : 01.02.2025
Department / Process Owner : Marketing & Development
Definition: Initial production control / initial flow management: Initial production control / initial flow management is a process of additional controls and monitoring by taking precautionary & preventive actions during the initial period of mass production of a new or changed part for a defined duration / quantity (pilot lot to the start of production). Person authorized to announce the start & end of initial production control / initial flow management is New product development head. | [6 empty] | Page 1 of 1
Step No. | Operation / Activity Description | Means/Device | Frequency | Record/Document | Responsibility | Reaction Plan | Photograph / Sketch, if applicable
1 | After SIR approval, take permission / plan for pilot production from the customer. Initial production control to be initiated / introduced after due approval of the PSW from customer / PPAP run with sufficient qty. manufacturing. | Mail / Courier / Letter | After pilot lot submission | Part Submission Warrant (PSW) (STPPL/QA/FM/17) | Officer Marketing / Marketing Process Owner | If any issue observed by customer then based on customer feedback initiate corrections | -
2 | Initial Production Control (IPC) lot needs to be inspected with special care as follows: a) Inspect the parts 200% for visual parameters and sampling inspection of the variable parameters as per control plan (Or follow inspection plan as specified /required by the customer). b) Statistical Process Control (Process Capability) of the part critical parameters. c) Process audit of the activities being performed (with referance to Control Plan). | Manual | a) Every Initial Production Lots. b) For every pilot lot & Once in a month for Intial Production Lots. c) For every Pilot lot & once in a month for Intial Production Lots. | Inprocess Inspection Report (STPPL/QA/FM/04), Sampling plan (STPPL/QA/FM/02), Statistical Process Control (STPPL/QA/FM/18) & Process Audit Sheet (STPPL / QA / FM / 27) | Q.A Process Owner & Project Leader / Development Engg. | - | -
3 | Inspection of the part by designated and trained operator / inspector. Training to be provided well before the pilot lot / PPAP run. | Manual | Each time of new product development / ECN / PCN | Training attendance sheet (STPPL/HRA/FM/06) | Project Leader / Development Engg. / HRA process owner | - | -
4 | Separate / dedicated work station duly equipped with all requirements as per the product specification under inspection / testing ( Inspection instruments, test equipments, work instructions,product specifications, inspection testing check sheet, skill matrix of the persons deployed, sampling plan, list of CTQ parameters, appropriate work environment condition etc.) | Manual | Each time of new product development / ECN / PCN | ---- | Project Leader / Development Engg. | - | -
5 | Special identification of the lot / batch, till the customer confirmation & storage of the parts in a Isolated area on the shop floor to avoid the mix-up & to have a special control. | Manual | Each time of Pilot lot submission | Initial Production Part Label (STPPL/MKD/LB/03) | Project Leader / Development Engg. | - | -
6 | Communicate pilot lot/Initial production control detail to the customer. To monitor and keep the record of production, inspection, dispatch, rejection, disposal of rejected parts etc. | Manual, Mail, Telephone | Each time of Pilot lot submission | Initial Production control details (STPPL/QA/FM/39) | Project Leader / Development Engg. | - | -
7 | If customer observe / notify any non conformity in the pilot lot / initial supplies, then resolve within 48 Hrs, with proper 8D / CAPA reporting. | Manual | Every Initial Production Lots | Customer Complaint Handling Form (8-D / CAPA Report) (STPPL/QA/FM/43) / Customer CA Format | Project Leader / Development Engg. & Project Team Members | - | -
8 | Continue & monitor this activity for next three months / qty. 5000 nos. in case of new product development and in case of ECN / PCN 1000 nos. of parts or 1 month, which ever is later, Initial Production Control will be terminated based on - a) Achievement of set targets at the time team feasibility activity, b) No defect at customer in last three months, c) No abnormal rejection/rework or breakdown, d) All the IFM action points (Part & Process related) are closed, e) Closure / Extension of IFM to be formally communicated from customer. | Mail, Telephone,Manual | After Pilot lot submission | Qty Tracking sheet (STPPL/MKD/FM/12) Project Handover sheet (STPPL/MKD/FM/15) | Project Leader / Development Engg. | - | -
9 | Initiation & Termination of the Initial Production Control is the responsibility of Development department head with consultation of project CFT members. | Manual | After Initial product lot submission | Project Handover sheet (STPPL/MKD/FM/15) | Devlopment department head & Project Team Members | -
10 | Hand over the project along with the all related documents, customer approved sample, Approved waviors if any, jigs, fixtures, gauges, qty. tracking sheet etc. | Manual | At the time of project handover | Project Handover sheet (STPPL/MKD/FM/15) Qty. Tracking sheet (STPPL/MKD/FM/12) | Project Leader / Development Engg. | - | -
11 | If initial production control / initial flow management termination controls conditions are not achived / fulfill, IPC termination/project handover period to series production to be extended by one month with identification of specific reasons and appropriate corrective measures. | Manual | At the time of project handover | Project Handover sheet (STPPL/MKD/FM/15) | Project Leader / Development Engg. | - | -
Review Date:- 01.02.2025 Review Due on:- 01.02.2026
Revision History :
Sr. | Revison in Document |  | Existing No. | Revised No. | Initiated by | Approved by | Prepared by :
1 | SPC frequency added |  | 00 | 01 | Gaurav | RUB
2 | IPC for ECN added, Sr.No.7 added, Sr.No5 Modified for 8D/CAPA, Scope & Defination modified,Logo added to header. |  | 01 | 02 / 24.01.17 | JBR | RUB
3 | Review & revised steps - Frequency, Record /Documents & Responsibility column. |  | 02 / 24.01.17 | 03 / 11.03.2019 | Vaibhav Pawar | R.U.Bhutekar
4 | Sr. No. 2 modified for inspection frequency (100% or 200% as per CP & customer spec. if any). Added qty. 3000 nos.in the activity serial no. 6. |  | 03 / 11.03.2019 | 04 / 01.09.2019 | Bhaiyya Patil | R.U.Bhutekar | Approved by :
5 | Sr. No. 2 modified for inspection frequency 100% for visual & sampling of variable parameters or as specified by the customer. |  | 04 / 01.09.2019 | 05 / 18.02.2020 | Bhaiyya Patil | R.U.Bhutekar
6 | Elaborated the defination of initial production control. |  | 05 / 18.02.2020 | 06 / 23.07.2021 | Umakanti Rajput | R.U.Bhutekar
7 | Revised scope, added rule for termination of IPC/IFM, revised rule for termination of ECN/PCN, added additional requirement of designated person, separate work station, 200% inspection for visual parameters etc. |  | 06 / 23.07.2021 | 07 / 01.01.2022 | Vandana Manchandani | R.U.Bhutekar
8 | Step no. 01 revised by elaborating the rule for initiation of initial production control. (PSW approval / sufficient qty. manufacturing in PPAP run). Step no. 08 revised for change in IPC termination rule as no customer complaint from last three months. |  | 07 / 01.01.2022 | 08 / 14.01.2022 | Vandana Manchandani | R.U.Bhutekar
9 | Review date row added and logo changed |  | 08 / 14.01.2022 | 09 / 04.02.2023 | C. Khose | R.U.Bhutekar
10 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  | 09 / 04.02.2023 | 09 / 01.02.2024 | A. Deshmukh | R.U.Bhutekar
11 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  | 09 / 01.02.2024 | 09 / 01.02.2025 | A. Deshmukh | R.U.Bhutekar