## SOP07-APQP
STPPL | Standard Operating Procedure |  | Purpose : To standardise the process of APQP. |  |  |  | STPPL/MKD/SOP/ 07
| Title : Advanced Product Quality Planning |  | Scope : Development of new product including STPLGN items. |  |  |  | Rev. No.: 07
Department / Process Owner : Marketing & development | [6 empty] | Rev date: 04.01.2021
Step No. | Operation / Activity Description | Means/Device | Frequency | Record / Document | Responsibility | Reaction Plan | Photograph / Sketch, if applicable
1 | Receive the Enquiry from customer in the form of Drawing / Sample. Log the enquiry in enquiry register. | Manual / Mail / Telephone / Courrier | Each time of enquiry | Enquiry Register (STPPL/MKD/FM/01) | Officer Marketing / Marketing Process Owner | Response time to new enquiry should be within two working days. | -
2 | Send the enquiry to tool maker, get the quotation from the tool makers. | Mail, Courier, by hand | Each time of Enquiry | Enquiry Register (STPPL/MKD/FM/01) & Quotation | Project Leader / Development Engg. | -
3 | Decide the feasibility on the basis of commercial things and scope for development and mark the comment in enquiry register. | Manual | Each time of Enquiry | Enquiry Register (STPPL/MKD/FM/01) Preliminary / Initial Feasibility Study (STPPL/MKD/FM/23) | Officer Marketing / Marketing Process Owner, Project Leader / Development Engg. & Project Team Members | In case customer does not specify exact requirement, CR will coordinate with customer for the same. | -
4 | If feasible, prepare the quotation of the component and send it to customer. | Manual / Mail / Courrier | Each time of Enquiry | Quotation (STPPL/MKD/FM/08) | Officer Marketing / Marketing Process Owner | If not feasibile, inform to customer. In case customer does not specify exact requirement, CR will coordinate with customer for the same.
5 | Take confirmation from customer in the form of Purchase order, LOI or any written communication. | Manual / Mail / Courrier | Each time of Enquiry | P.O in Customer Format, LOI, Written communication. | Officer Marketing / Marketing Process Owner | - | -
6 | Form the CFT for APQP and take team feasibility comittment by technical and other required studies. Risk analysis to be done at the time of Feasibility. (Involvement of interested parties like customer, supplier, service provider etc. at the propriate stages of project management to be considered and to be involved during the appropriate stages of the project management). | Manual | Each time of product development | Team Feasibility Commitment (STPPL/MKD/FM/02) | Project Leader / Development Engg. & Project Team Members | - | -
7 | Prepare the APQP Time plan chart to monitor & control the activities as per time line. | After receiving conformation from customer in the form of P.O, LOI or any written communication. | Each time of product development | APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. | - | -
8 | Review, distribution, and implementation of all customer engineering specifications and related revisions based on customer schedules, as required. | Manual / Mail | Each time of product development | - | Project Leader / Development Engg. | - | -
9 | Review APQP time plan periodically and initiate the necessary approprite actions on the problem determine with verification and validation. | Manual | Each time of product development | APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. & Project Team Members | - | -
10 | If any concerns raised in the CFT meeting for feasibility commitment then inform to customer about those concerns. | mail,letter. | Each time of product development | APQP Time -Plan chart (STPPL/MKD/FM/03) Cross Functional Team For APQP (STPPL/MKD/FM/11) | Project Leader / Development Engg. & Officer Marketing / Marketing Process Owner | - | -
11 | After receipt of confirmation from customer, prepare PFD , PFMEA & Prelaunch Control Plan | Manual | Each time of product development | PFD (STPPL/QA/FM /21) PFMEA (STPPL/QA/FM/13) Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
12 | Raise the P.O. for tool maker along with Annexure to P.O. for Tool Making and go ahead for the development. Collect the acknowledgement copy for the same. | Manual / Mail / Courrier | Each time of product development | Purchase Order (STPPL/PUR/FM/02) Anexure to P.O. for Tool Making (STPPL/MKD/FM/09) Supplier Acknowledgement | Purchase Process Owner & Project Leader / Development Engg. | - | -
13 | Monitor & update Mould Development Time Plan on weekly basis. Collect activity completion evidences from supplier as per decided time plan. including Jig Fixture development. | Manual / Mail / Courrier | Weekly basis, At the time of tool development | APQP Time -Plan chart (STPPL/MKD/FM/03) Mould Development Time Plan (STPPL/MKD/FM/22) | Project Leader / Development Engg. | If any activity not completed as per decided time plan, then take actions plan & target date from suppliers for delays. | -
14 | As per Mould Development Time Plan, demand & receive mould design from tool maker. Discuss the received mould design and cross check the same as per our requirement. If required, mould design discuss with customer also (in case of customer approval). | Manual / Mail / Courrier | At the time of tool development | Mould Development Time Plan (STPPL/MKD/FM/22) 3D CAD Data Tool Design Review Check Sheet (STPPL/MKD/FM/17) | Project Leader & Project Team Members | Inform Tool maker if there is any problem in the mould design and get the mould design corrected. | -
15 | After mould development, inspect the mould as per Mould Inspection Check Sheet before conduct the trial. | Manual | After tool development & before trial | Mould Inspection Check Sheet (STPPL/MKD/FM/13) | Project Leader / Development Engg. | - | -
16 | Make the proper arrangement for trial of mould Take the Trial and keep the samples in P.D. after trial completion. | Manual | Each time | Trial Requisition Note (STPPL/MKD/FM/06) Trial Report (STPPL/MKD/FM/16) APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. | Inform to customer if trial not taken on the planned date and arrange for the trial at the earliest. | -
17 | Inspect the samples and prepare the SIR. | Manual | After T0 trial | Sample Inspection Report (STPPL/QA/FM/11) | Project Leader / Development Engg. | Inform Tool maker if there is any problem in the mould and get the mould corrceted. | -
18 | Send the samples through courier for outside customer or give by hand for local customer. And convey the details to customer | Manual / Courier | At the time of sample submission | Sample Inspection Report (STPPL/QA/FM/11) Covering Letter Material TC | Project Leader / Development Engg. | - | -
19 | Ensure the customer product approval on the sample submitted. Also ensure that product / process is approved by the customer prior to shipment of the lot. | Manual / Mail / Courier | After sample submission | Customer SIR / Customer written communication. | Project Leader / Development Engg. | - | -
20 | Conduct SPC, MSA, Operator training as aplicable etc. at appropriate stage. | Manual | During IPC. | SPC,MSA & training record. | Project Leader / Development Engg. | - | -
21 | Submit the pilot lot as per requirement along with the PPAP. | Manual / Transport | After Product approval | PPAP document | Project Leader / Development Engg. & Project Team Members | - | -
22 | Take the feedback from customer, get the approved PSW from customer. | Mail / Courier / Letter | After pilot lot submission | Part Submission Warrant (PSW) (STPPL/QA/FM/17) | Officer Marketing / Marketing Process Owner | If any issue observed by customer then based on customer feedback initiate corrections | -
23 | Proceed Initial production control activity as per laiddown procedure, for next three months. | Manual | After pilot lot Approval / PSW Approval | SOP- Initial Production control (STPPL/MKD/SOP/16) | Project Leader / Development Engg. & Project Team Members | - | -
24 | Project hand over / Termination to be based on customer target achievements along with the all related documents, customer approved sample, Approved waviours if any, jigs, fixtures, gauges, qty. tracking sheet etc. | Manual | At the time of project handover | Project Handover sheet (STPPL / MKD / FM / 15) Qty. Tracking sheet (STPPL/MKD/FM/12) | Project Leader / Development Engg. | - | -
25 | CFT meeting for review of complete project to make summary of things went wrong & lesson learnt. The out put for improvements will be used for next project improvements. | Manual | At the time of project handover | Lesson Learnt sheet (STPPL/MKD/FM/20) | Project Leader / Development Engg. & Project Team Members | - | -
APQP Review
1 | Development status review with Project Team Members detail, defined actions for delayed activities if any, maintain seperately in Cross Functional Team For APQP format. | Manual | Weekly | APQP Time -Plan chart (STPPL/MKD/FM/03) Cross Functional Team For APQP (STPPL/MKD/FM/11) | Project Leader / Development Engg. & Project Team Members | Deciding actions for issues/delayed activities if any | -
Revision History :
Sr. | Revision in Document |  | Existing No. | Revised No. | Initiated by | Approved by | Prepared by :
1 | Periodic APQP review freqency added, Step sequence revised for PFD, PFMEA, Logo added to Header. |  | 2 | 3 / 23.01.17 | JBR | R.U.Bhutekar
2 | Sr. No. 8 and 9 added for review distribution of engineering specification and review of APQP time plan. |  | 3 / 23.01.17 | 4 / 01.03.2018 | Vaibhav Pawar | R.U.Bhutekar
3 | Added Step No.- 14 & 15, Edited Step No.- 01,12,13,19,20,23,24. Also review & revised steps - Means /device, Frequency, Record /Documents, Responsibility & reaction plan etc.column. |  | 4 / 01.03.2018 | 5 / 11.03.2019 | Vaibhav Pawar | R.U.Bhutekar
4 | Added Step No.- 20 ( SPC,MSA & Training etc.) |  | 5 / 11.03.2019 | 6 / 1.09.2019 | Bhaiya Patil. | R.U.Bhutekar | Approved by :
5 | Step no. 6 revised by capturing the involvement of interested parties in project management. |  | 6 / 1.09.2019 | 7 / 04.01.2021 | Vandana Manchandani | R.U.Bhutekar

## SOP07-APQP rev.08
STPPL | Standard Operating Procedure |  | Purpose : To standardise the process of APQP. |  |  |  | STPPL/MKD/SOP/ 07
| Title : Advanced Product Quality Planning |  | Scope : Development of new product / service development. |  |  |  | Rev. No.: 08
Department / Process Owner : Marketing & development | [6 empty] | Rev date: 28.07.2021
Step No. | Operation / Activity Description | Means/Device | Frequency | Record / Document | Responsibility | Reaction Plan | Photograph / Sketch, if applicable
1. Plan & define
1 | Receipt of enquiry from customer in the form of drawing / standard / Sample / other information. Log the enquiry in enquiry register. | Manual / Mail / Telephone / Courrier | Each time of enquiry | Enquiry Register (STPPL/MKD/FM/01) | Officer Marketing / Marketing Process Owner | Response time to new enquiry should be within two working days. | -
2 | Form a CFT for the new product / service requirement review and conclude on manufacturing feasibility. Intimate to the customer accordingly. | Manual | Each time of enquiry | CFT for APQP (STPPL/MKD/FM/11) & Preliminary feasibility (STPPL/MKD/FM/23) | Project Leader / Development Engg. | - | -
3 | If any concerns raised in the CFT meeting for feasibility commitment then inform to customer about those concerns. | mail,letter. | Each time of product development | CFT for APQP (STPPL/MKD/FM/11) | Project Leader / Development Engg. & Officer Marketing / Marketing Process Owner | - | -
4 | Send the enquiry to tool / fixture / gauge / equipment manufacturer and get the quotation. | Mail, Courier, by hand | Each time of Enquiry | Quotation | Project Leader / Development Engg. / Purchase process owner | - | -
5 | Decide the feasibility on the basis of commercial things and scope for development and mark the comment in enquiry register. | Manual | Each time of Enquiry | Enquiry Register (STPPL/MKD/FM/01) Preliminary / Initial Feasibility Study (STPPL/MKD/FM/23) | Officer Marketing / Marketing Process Owner, Project Leader / Development Engg. & Project Team Members | In case customer does not specify exact requirement, CR will coordinate with customer for the same. | -
6 | If feasible, prepare the quotation of the component and send it to customer. | Manual / Mail / Courrier | Each time of Enquiry | Quotation (STPPL/MKD/FM/08) | Officer Marketing / Marketing Process Owner | If not feasibile, inform to customer. In case customer does not specify exact requirement, CR will coordinate with customer for the same.
7 | Take confirmation from customer in the form of Purchase order, LOI or any written communication. | Manual / Mail / Courrier | Each time of Enquiry | P.O in Customer Format, LOI, Written communication. | Officer Marketing / Marketing Process Owner | - | -
8 | Issue the P.O to tool / fixture / gauge / equipment manufacturer. (tool P.O with detailed annexture) | Manual / Mail / Courrier | Each enquiry as applicable | Supplier P.O | Purchase Process Owner & Project Leader / Development Engg. | - | -
9 | Monitor & update Mould Development Time Plan on weekly basis. Collect activity completion evidences from supplier as per decided time plan. including Jig Fixture development. | Manual / Mail / Courrier | Weekly basis, At the time of tool development | APQP Time -Plan chart (STPPL/MKD/FM/03) Mould Development Time Plan (STPPL/MKD/FM/22) | Project Leader / Development Engg. | If any activity not completed as per decided time plan, then take actions plan & target date from suppliers for delays. | -
10 | As per Mould Development Time Plan, demand & receive mould design from tool maker. Discuss the received mould design and cross check the same as per our requirement. If required, mould design discuss with customer also (in case of customer approval). | Manual / Mail / Courrier | At the time of tool development | Mould Development Time Plan (STPPL/MKD/FM/22) 3D CAD Data Tool Design Review Check Sheet (STPPL/MKD/FM/17) | Project Leader & Project Team Members | Inform Tool maker if there is any problem in the mould design and get the mould design corrected. | -
11 | Prepare the APQP responsibility matrix & time plan chart to monitor & control the activities as per time line. | After receiving conformation from customer in the form of P.O, LOI or any written communication. | Each time of product development | APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. | - | -
12 | Form the CFT for APQP and take team feasibility comittment by technical and other required studies. Risk analysis to be done at the time of Feasibility. (Involvement of interested parties like customer, supplier, service provider etc. at the propriate stages of project management to be considered and to be involved during the appropriate stages of the project management). | Manual | Each time of product development | Team Feasibility Commitment (STPPL/MKD/FM/02) | Project Leader / Development Engg. & Project Team Members | - | -
13 | Identify the special characteristics (product & process). | Manual | Each time of product development | Special characteristics matrix (STPPL/MKD/FM/18) | CFT | - | -
14 | Preparation of preliminary bill of material & process flow diagram. | Manual | Each time of product development | Process flow diagram (STPPL/QA/FM/21) | Project Leader / Development Engg. & Project Team Members | - | -
15 | Get the micro time plan for tool / fixture / gauge / equipment development from supplier and review the development status periodically. | Manual | As & when required | - | Project Leader / Development Engg. | - | -
16 | Review, distribution, and implementation of all customer engineering specifications and related revisions based on customer schedules, as required. | Manual / Mail | Each time of product development | Control of technical specification (STPPL/MKD/FM/25) | Project Leader / Development Engg. | - | -
2. Product design & development (not product design responsible)
17 | Detail review of design requirements related to tool / jig / fixture / gauge / equipment. To identify & record the special characteristics of product & process. | Manual | Each time of product development | Team Feasibility Commitment (STPPL/MKD/FM/02) & Special characteristics matrix (STPPL/MKD/FM/18) | Project Leader / Development Engg. & Project Team Members | - | -
3. Process design & development
18 | After receipt of confirmation from customer, prepare PFD, PFMEA & Control Plan (proto / prelaunch as applicable). | Manual | Each time of product development | PFD (STPPL/QA/FM /21) PFMEA (STPPL/QA/FM/13) Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
19 | Prepare the plan for MSA & process capability study. | Manual | Each time of product development | Plan for MSA (STPPL/QA/FM/23) & SPC plan (STPPL/QA/FM/38) | Project Leader / Development Engg. | - | -
20 | Preparation of process instruction (WI) and packaging standard / specification. | Manual | Each time of product development | Product specific WI & packing standard | Project Leader / Development Engg. | - | -
21 | Provide appropriate necessary training to concerned person's related to new product & process. | Manual | As & when required | Training attendance sheet (STPPL/HRA/FM/06) | Project Leader / Development Engg. | - | -
4. Product & process validation
22 | After tool development, inspect the mould as per Mould Inspection Check Sheet before conduct the trial. Inspection & testing of the jig / fixture / gauge / other equipment as per the requirement. | Manual | After tool development & before trial | Mould Inspection Check Sheet (STPPL/MKD/FM/13) & Jig / fixture / gauges / equipment inspection record. | Project Leader / Development Engg. | - | -
23 | Make the proper arrangement for trial of mould (T0 to Tfinal). Take the trial and keep the samples in product development after trial completion. | Manual | Each time | Trial Requisition Note (STPPL/MKD/FM/06) Trial Report (STPPL/MKD/FM/16) APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. | Inform to customer if trial not taken on the planned date and arrange for the trial at the earliest. | -
24 | Inspect the samples and prepare the SIR. | Manual | After T0 trial | Sample Inspection Report (STPPL/QA/FM/11) | Project Leader / Development Engg. | Inform Tool maker if there is any problem in the mould and get the mould corrceted. | -
25 | Send the samples through courier for outside customer and give by hand for local customer. And convey the details to customer. | Manual / Courier | At the time of sample submission | Sample Inspection Report (STPPL/QA/FM/11) Covering Letter Material TC | Project Leader / Development Engg. | - | -
26 | Ensure the customer product approval on the sample submitted. Also ensure that product / process is approved by the customer prior to shipment of the lot. | Manual / Mail / Courier | After sample submission | Customer SIR / Customer written communication. | Project Leader / Development Engg. | If demanded by customer, correction to be done in tool / part. | -
27 | Prepare pilot lot and conduct process capability study, MSA study and packaging evalaution. | Manual | After sample approval | SPC (STPPL/QA/FM/18) & MSA (STPPL/QA/FM/19) | Project Leader / Development Engg. | - | -
28 | Submit the pilot lot to customer & get the feedback. | Manual | After sample approval | PDI report (STPPL/QA/FM/01) | Project Leader / Development Engg. | If demanded by customer, correction to be done in tool / part. | -
29 | Review the design goals & target i.e. productivity, rejection PPM, capability study, RPN etc. | Manual | After pilot lot | MOM | Project Leader / Development Engg. & Project Team Members | - | -
30 | Prepare the PPAP lot and finalize the process documents (PFD, PFMEA, CP, WI, SPPS etc). | Manual | After pilot lot submission | PPAP documents | Project Leader / Development Engg. & Project Team Members | - | -
31 | Submit the PPAP lot to customer & get approved PSW from customer. | Manual | After PPAP lot submission | PSW | Project Leader / Development Engg. | If any issue observed by customer then based on customer feedback initiate corrections | -
32 | Proceed Initial production control activity as per laiddown procedure. (3000 nos. or time duration of 3 months, whiever is later). | Manual | After pilot lot Approval / PSW Approval | SOP- Initial Production control (STPPL/MKD/SOP/16) & Qty. Tracking sheet (STPPL/MKD/FM/12) | Project Leader / Development Engg. & Project Team Members | - | -
33 | Project hand over / Termination to be based on customer target achievements along with the all related documents, customer approved sample, Approved waviours if any, jigs, fixtures, gauges, qty. tracking sheet etc. | Manual | At the time of project handover | Project Handover sheet (STPPL / MKD / FM / 15) Qty. Tracking sheet (STPPL/MKD/FM/12) | Project Leader / Development Engg. | - | -
5. Feedback analysis & corrective action
34 | CFT meeting for review of complete project to make summary of things went right, wrong & lesson learnt. The out put for improvements will be used for next project improvements. | Manual | At the time of project handover | Lesson Learnt sheet (STPPL/MKD/FM/20) | Project Leader / Development Engg. & Project Team Members | - | -
APQP Review
35 | Review APQP time plan periodically and initiate the necessary approprite actions on the problem determine with verification and validation. | Manual | Each time of product development | APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. & Project Team Members | - | -
Revision History :
Sr. | Revision in Document |  | Existing No. | Revised No. | Initiated by | Approved by | Prepared by :
1 | Periodic APQP review freqency added, Step sequence revised for PFD, PFMEA, Logo added to Header. |  | 2 | 3 / 23.01.17 | JBR | R.U.Bhutekar
2 | Sr. No. 8 and 9 added for review distribution of engineering specification and review of APQP time plan. |  | 3 / 23.01.17 | 4 / 01.03.2018 | Vaibhav Pawar | R.U.Bhutekar
3 | Added Step No.- 14 & 15, Edited Step No.- 01,12,13,19,20,23,24. Also review & revised steps - Means /device, Frequency, Record /Documents, Responsibility & reaction plan etc.column. |  | 4 / 01.03.2018 | 5 / 11.03.2019 | Vaibhav Pawar | R.U.Bhutekar
4 | Added Step No.- 20 ( SPC,MSA & Training etc.) |  | 5 / 11.03.2019 | 6 / 1.09.2019 | Bhaiya Patil. | R.U.Bhutekar | Approved by :
5 | Step no. 6 revised by capturing the involvement of interested parties in project management. |  | 6 / 1.09.2019 | 7 / 04.01.2021 | Vandana Manchandani | R.U.Bhutekar
5 | Activities organized as per the phases of APQP. |  | 7 / 04.01.2021 | 08 / 28.07.2021 | Umakanti Rajput | R.U.Bhutekar

## SOP07-APQP rev.09
STPPL | Standard Operating Procedure |  | Purpose : To standardise the process of APQP. |  |  |  | STPPL/MKD/SOP/ 07
| Title : Advanced Product Quality Planning |  | Scope : Development of new product / service development. |  |  |  | Rev. No.: 09
Department / Process Owner : Marketing & development | [6 empty] | Rev date: 04.09.2021
Step No. | Operation / Activity Description | Means/Device | Frequency | Record / Document | Responsibility | Reaction Plan | Photograph / Sketch, if applicable
1. Plan & define
1 | Receipt of enquiry from customer in the form of drawing / standard / Sample / other information. Log the enquiry in enquiry register. | Manual / Mail / Telephone / Courrier | Each time of enquiry | Enquiry Register (STPPL/MKD/FM/01) | Officer Marketing / Marketing Process Owner | Response time to new enquiry should be within two working days. | -
2 | Form a CFT for the new product / service requirement review and conclude on manufacturing feasibility. Intimate to the customer accordingly. | Manual | Each time of enquiry | CFT for APQP (STPPL/MKD/FM/11) & Preliminary feasibility (STPPL/MKD/FM/23) | Project Leader / Development Engg. | - | -
3 | If any concerns raised in the CFT meeting for feasibility commitment then inform to customer about those concerns. | mail,letter. | Each time of product development | CFT for APQP (STPPL/MKD/FM/11) | Project Leader / Development Engg. & Officer Marketing / Marketing Process Owner | - | -
4 | Send the enquiry to tool / fixture / gauge / equipment manufacturer and get the quotation. | Mail, Courier, by hand | Each time of Enquiry | Quotation | Project Leader / Development Engg. / Purchase process owner | - | -
5 | Decide the feasibility on the basis of commercial things and scope for development and mark the comment in enquiry register. | Manual | Each time of Enquiry | Enquiry Register (STPPL/MKD/FM/01) Preliminary / Initial Feasibility Study (STPPL/MKD/FM/23) | Officer Marketing / Marketing Process Owner, Project Leader / Development Engg. & Project Team Members | In case customer does not specify exact requirement, CR will coordinate with customer for the same. | -
6 | If feasible, prepare the quotation of the component and send it to customer. | Manual / Mail / Courrier | Each time of Enquiry | Quotation (STPPL/MKD/FM/08) | Officer Marketing / Marketing Process Owner | If not feasibile, inform to customer. In case customer does not specify exact requirement, CR will coordinate with customer for the same.
7 | Take confirmation from customer in the form of Purchase order, LOI or any written communication. | Manual / Mail / Courrier | Each time of Enquiry | P.O in Customer Format, LOI, Written communication. | Officer Marketing / Marketing Process Owner | - | -
8 | Issue the P.O to tool / fixture / gauge / equipment manufacturer. (tool P.O with detailed annexture) | Manual / Mail / Courrier | Each enquiry as applicable | Supplier P.O | Purchase Process Owner & Project Leader / Development Engg. | - | -
9 | Monitor & update Mould Development Time Plan on weekly basis. Collect activity completion evidences from supplier as per decided time plan. including Jig Fixture development. | Manual / Mail / Courrier | Weekly basis, At the time of tool development | APQP Time -Plan chart (STPPL/MKD/FM/03) Mould Development Time Plan (STPPL/MKD/FM/22) | Project Leader / Development Engg. | If any activity not completed as per decided time plan, then take actions plan & target date from suppliers for delays. | -
10 | As per Mould Development Time Plan, demand & receive mould design from tool maker. Discuss the received mould design and cross check the same as per our requirement. If required, mould design discuss with customer also (in case of customer approval). | Manual / Mail / Courrier | At the time of tool development | Mould Development Time Plan (STPPL/MKD/FM/22) 3D CAD Data Tool Design Review Check Sheet (STPPL/MKD/FM/17) | Project Leader & Project Team Members | Inform Tool maker if there is any problem in the mould design and get the mould design corrected. | -
11 | Prepare the APQP responsibility matrix & time plan chart to monitor & control the activities as per time line. | After receiving conformation from customer in the form of P.O, LOI or any written communication. | Each time of product development | APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. | - | -
12 | Form the CFT for APQP and take team feasibility comittment by technical and other required studies. Risk analysis to be done at the time of Feasibility. (Involvement of interested parties like customer, supplier, service provider etc. at the propriate stages of project management to be considered and to be involved during the appropriate stages of the project management). | Manual | Each time of product development | Team Feasibility Commitment (STPPL/MKD/FM/02) | Project Leader / Development Engg. & Project Team Members | - | -
13 | Identify the special characteristics (product & process). | Manual | Each time of product development | Special characteristics matrix (STPPL/MKD/FM/18) | CFT | - | -
14 | Preparation of preliminary bill of material & process flow diagram. | Manual | Each time of product development | Process flow diagram (STPPL/QA/FM/21) | Project Leader / Development Engg. & Project Team Members | - | -
15 | Get the micro time plan for tool / fixture / gauge / equipment development from supplier and review the development status periodically. | Manual | As & when required | - | Project Leader / Development Engg. | - | -
16 | Review, distribution, and implementation of all customer engineering specifications and related revisions based on customer schedules, as required. | Manual / Mail | Each time of product development | Control of technical specification (STPPL/MKD/FM/25) | Project Leader / Development Engg. | - | -
2. Product design & development (not product design responsible)
17 | Detail review of design requirements related to tool / jig / fixture / gauge / equipment. To identify & record the special characteristics of product & process. | Manual | Each time of product development | Team Feasibility Commitment (STPPL/MKD/FM/02) & Special characteristics matrix (STPPL/MKD/FM/18) | Project Leader / Development Engg. & Project Team Members | - | -
3. Process design & development
18 | After receipt of confirmation from customer, prepare PFD, PFMEA & Control Plan (proto / prelaunch as applicable). | Manual | Each time of product development | PFD (STPPL/QA/FM /21) PFMEA (STPPL/QA/FM/13) Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
19 | Prepare the plan for MSA & process capability study. | Manual | Each time of product development | Plan for MSA (STPPL/QA/FM/23) & SPC plan (STPPL/QA/FM/38) | Project Leader / Development Engg. | - | -
20 | Preparation of process instruction (WI) and packaging standard / specification. | Manual | Each time of product development | Product specific WI & packing standard | Project Leader / Development Engg. | - | -
21 | Provide appropriate necessary training to concerned person's related to new product & process. | Manual | As & when required | Training attendance sheet (STPPL/HRA/FM/06) | Project Leader / Development Engg. | - | -
4. Product & process validation
22 | After tool development, inspect the mould as per Mould Inspection Check Sheet before conduct the trial. Inspection & testing of the jig / fixture / gauge / other equipment as per the requirement. | Manual | After tool development & before trial | Mould Inspection Check Sheet (STPPL/MKD/FM/13) & Jig / fixture / gauges / equipment inspection record. | Project Leader / Development Engg. | - | -
23 | Make the proper arrangement for trial of mould (T0 to Tfinal). Take the trial and keep the samples in product development after trial completion. | Manual | Each time | Trial Requisition Note (STPPL/MKD/FM/06) Trial Report (STPPL/MKD/FM/16) APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. | Inform to customer if trial not taken on the planned date and arrange for the trial at the earliest. | -
24 | Inspect the samples and prepare the SIR. | Manual | After T0 trial | Sample Inspection Report (STPPL/QA/FM/11) | Project Leader / Development Engg. | Inform Tool maker if there is any problem in the mould and get the mould correceted. | -
25 | Send the samples through courier for outside customer and give by hand for local customer. And convey the details to customer. | Manual / Courier | At the time of sample submission | Sample Inspection Report (STPPL/QA/FM/11) Covering Letter Material TC | Project Leader / Development Engg. | - | -
26 | Ensure the customer product approval on the sample submitted. Also ensure that product / process is approved by the customer prior to shipment of the lot. | Manual / Mail / Courier | After sample submission | Customer SIR / Customer written communication. | Project Leader / Development Engg. | If demanded by customer, correction to be done in tool / part. | -
27 | Prepare pilot lot and conduct process capability study, MSA study and packaging evalaution. | Manual | After sample approval | SPC (STPPL/QA/FM/18) & MSA (STPPL/QA/FM/19) | Project Leader / Development Engg. | - | -
28 | Submit the pilot lot to customer & get the feedback. | Manual | After sample approval | PDI report (STPPL/QA/FM/01) | Project Leader / Development Engg. | If demanded by customer, correction to be done in tool / part. | -
29 | Review the design goals & target i.e. productivity, rejection PPM, capability study, RPN etc. | Manual | After pilot lot | MOM | Project Leader / Development Engg. & Project Team Members | - | -
30 | Prepare the PPAP lot and finalize the process documents (PFD, PFMEA, CP, WI, SPPS etc). | Manual | After pilot lot submission | PPAP documents | Project Leader / Development Engg. & Project Team Members | - | -
31 | Submit the PPAP lot to customer & get approved PSW from customer. | Manual | After PPAP lot submission | PSW | Project Leader / Development Engg. | If any issue observed by customer then based on customer feedback initiate corrections | -
32 | Proceed Initial production control activity as per laiddown procedure. (3000 nos. or time duration of 3 months, whichever is later). | Manual | After pilot lot Approval / PSW Approval | SOP- Initial Production control (STPPL/MKD/SOP/16) & Qty. Tracking sheet (STPPL/MKD/FM/12) | Project Leader / Development Engg. & Project Team Members | - | -
33 | Review the manufacturing process design output against manufacturing process design inputs. | Manual | Before project handover | Manufacturing process design output verification (STPPL/MKD/FM/27) | Project Leader / Development Engg. & Project Team Members | If any target not achieved / met, action to be initiate. | -
34 | Project hand over / Termination to be based on customer target achievements along with the all related documents, customer approved sample, Approved waviours if any, jigs, fixtures, gauges, qty. tracking sheet etc. | Manual | At the time of project handover | Project Handover sheet (STPPL / MKD / FM / 15) Qty. Tracking sheet (STPPL/MKD/FM/12) | Project Leader / Development Engg. | - | -
5. Feedback analysis & corrective action
35 | CFT meeting for review of complete project to make summary of things went right, wrong & lesson learnt. The out put for improvements will be used for next project improvements. | Manual | At the time of project handover | Lesson Learnt sheet (STPPL/MKD/FM/20) | Project Leader / Development Engg. & Project Team Members | - | -
APQP Review
36 | Review APQP time plan periodically and initiate the necessary approprite actions on the problem determine with verification and validation. | Manual | Each time of product development | APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. & Project Team Members | - | -
Revision History :
Sr. | Revision in Document |  | Existing No. | Revised No. | Initiated by | Approved by | Prepared by :
1 | Periodic APQP review freqency added, Step sequence revised for PFD, PFMEA, Logo added to Header. |  | 2 | 3 / 23.01.17 | JBR | R.U.Bhutekar
2 | Sr. No. 8 and 9 added for review distribution of engineering specification and review of APQP time plan. |  | 3 / 23.01.17 | 4 / 01.03.2018 | Vaibhav Pawar | R.U.Bhutekar
3 | Added Step No.- 14 & 15, Edited Step No.- 01,12,13,19,20,23,24. Also review & revised steps - Means /device, Frequency, Record /Documents, Responsibility & reaction plan etc.column. |  | 4 / 01.03.2018 | 5 / 11.03.2019 | Vaibhav Pawar | R.U.Bhutekar
4 | Added Step No.- 20 ( SPC,MSA & Training etc.) |  | 5 / 11.03.2019 | 6 / 1.09.2019 | Bhaiya Patil. | R.U.Bhutekar | Approved by :
5 | Step no. 6 revised by capturing the involvement of interested parties in project management. |  | 6 / 1.09.2019 | 7 / 04.01.2021 | Vandana Manchandani | R.U.Bhutekar
6 | Activities organized as per the phases of APQP. |  | 7 / 04.01.2021 | 08 / 28.07.2021 | Umakanti Rajput | R.U.Bhutekar
7 | Added step no. 33 - review of manufacturing process design output. |  | 08 / 28.07.2021 | 09 / 04.09.2021 | Vandana Manchandani | R.U.Bhutekar

## SOP07-APQP rev.10
STPPL | Standard Operating Procedure |  | Purpose : To standardise the process of APQP (Production preparation). |  |  |  | STPPL/MKD/SOP/ 07
| Title : Advanced Product Quality Planning (Production preparation) |  | Scope : Development of new product / service development. |  |  |  | Rev. No.: 10
Department / Process Owner : Marketing & development | [6 empty] | Rev date: 20.11.2021
Step No. | Operation / Activity Description | Means/Device | Frequency | Record / Document | Responsibility | Reaction Plan | Photograph / Sketch, if applicable
1. Plan & define
1 | Receipt of enquiry from customer in the form of drawing / standard / Sample / other information. Log the enquiry in enquiry register. | Manual / Mail / Telephone / Courrier | Each time of enquiry | Enquiry Register (STPPL/MKD/FM/01) | Officer Marketing / Marketing Process Owner | Response time to new enquiry should be within two working days. | -
2 | Form a CFT for the new product / service requirement review and conclude on manufacturing feasibility. Intimate to the customer accordingly. | Manual | Each time of enquiry | CFT for APQP (STPPL/MKD/FM/11) & Preliminary feasibility (STPPL/MKD/FM/23) | Project Leader / Development Engg. | - | -
3 | If any concerns raised in the CFT meeting for feasibility commitment then inform to customer about those concerns. | mail,letter. | Each time of product development | CFT for APQP (STPPL/MKD/FM/11) | Project Leader / Development Engg. & Officer Marketing / Marketing Process Owner | - | -
4 | Send the enquiry to tool / fixture / gauge / equipment manufacturer and get the quotation. | Mail, Courier, by hand | Each time of Enquiry | Quotation | Project Leader / Development Engg. / Purchase process owner | - | -
5 | Decide the feasibility on the basis of commercial things and scope for development and mark the comment in enquiry register. | Manual | Each time of Enquiry | Enquiry Register (STPPL/MKD/FM/01) Preliminary / Initial Feasibility Study (STPPL/MKD/FM/23) | Officer Marketing / Marketing Process Owner, Project Leader / Development Engg. & Project Team Members | In case customer does not specify exact requirement, CR will coordinate with customer for the same. | -
6 | If feasible, prepare the quotation of the component and send it to customer. | Manual / Mail / Courrier | Each time of Enquiry | Quotation (STPPL/MKD/FM/08) | Officer Marketing / Marketing Process Owner | If not feasibile, inform to customer. In case customer does not specify exact requirement, CR will coordinate with customer for the same.
7 | Take confirmation from customer in the form of Purchase order, LOI or any written communication. | Manual / Mail / Courrier | Each time of Enquiry | P.O in Customer Format, LOI, Written communication. | Officer Marketing / Marketing Process Owner | - | -
8 | Preparation of micro plan for procurement of tool / fixture / jig / gauge etc. Issue the P.O to tool / fixture / gauge / equipment manufacturer. (tool P.O with detailed annexture) | Manual / Mail / Courrier | Each enquiry as applicable | Supplier P.O | Purchase Process Owner & Project Leader / Development Engg. | - | -
9 | Monitor & update micro time plan on weekly basis. Collect activity completion evidences from supplier as per decided time plan. | Manual / Mail / Courrier | Weekly basis, At the time of tool development | APQP Time -Plan chart (STPPL/MKD/FM/03) Mould Development Time Plan (STPPL/MKD/FM/22) | Project Leader / Development Engg. | If any activity not completed as per decided time plan, then take actions plan & target date from suppliers for delays. | -
10 | As per Mould Development Time Plan, demand & receive mould design from tool maker. Discuss the received mould design and cross check the same as per our requirement. If required, mould design discuss with customer also (in case of customer approval). | Manual / Mail / Courrier | At the time of tool development | Mould Development Time Plan (STPPL/MKD/FM/22) 3D CAD Data Tool Design Review Check Sheet (STPPL/MKD/FM/17) | Project Leader & Project Team Members | Inform Tool maker if there is any problem in the mould design and get the mould design corrected. | -
11 | Prepare the APQP responsibility matrix & time plan chart to monitor & control the activities as per time line. | After receiving conformation from customer in the form of P.O, LOI or any written communication. | Each time of product development | APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. | - | -
12 | Form the CFT for APQP and take team feasibility comittment by technical and other required studies. Risk analysis to be done at the time of Feasibility. (Involvement of interested parties like customer, supplier, service provider etc. at the propriate stages of project management to be considered and to be involved during the appropriate stages of the project management). | Manual | Each time of product development | Team Feasibility Commitment (STPPL/MKD/FM/02) | Project Leader / Development Engg. & Project Team Members | - | -
13 | Identify the special characteristics (product & process). | Manual | Each time of product development | Special characteristics matrix (STPPL/MKD/FM/18) | CFT | - | -
14 | Preparation of preliminary bill of material & process flow diagram. | Manual | Each time of product development | Process flow diagram (STPPL/QA/FM/21) | Project Leader / Development Engg. & Project Team Members | - | -
15 | Get the micro time plan for tool / fixture / gauge / equipment development from supplier and review the development status periodically. | Manual | As & when required | - | Project Leader / Development Engg. | - | -
16 | Review, distribution, and implementation of all customer engineering specifications and related revisions based on customer schedules, as required. | Manual / Mail | Each time of product development | Control of technical specification (STPPL/MKD/FM/25) | Project Leader / Development Engg. | - | -
2. Product design & development (not product design responsible)
17 | Detail review of design requirements related to tool / jig / fixture / gauge / equipment. To identify & record the special characteristics of product & process. | Manual | Each time of product development | Team Feasibility Commitment (STPPL/MKD/FM/02) & Special characteristics matrix (STPPL/MKD/FM/18) | Project Leader / Development Engg. & Project Team Members | - | -
3. Process design & development
18 | After receipt of confirmation from customer, prepare PFD, PFMEA & Control Plan (proto / prelaunch as applicable). | Manual | Each time of product development | PFD (STPPL/QA/FM /21) PFMEA (STPPL/QA/FM/13) Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
19 | Prepare the plan for MSA & process capability study. | Manual | Each time of product development | Plan for MSA (STPPL/QA/FM/23) & SPC plan (STPPL/QA/FM/38) | Project Leader / Development Engg. | - | -
20 | Preparation of process instruction (WI) and packaging standard / specification. | Manual | Each time of product development | Product specific WI & packing standard | Project Leader / Development Engg. | - | -
21 | Provide appropriate necessary training to concerned person's related to new product & process. | Manual | As & when required | Training attendance sheet (STPPL/HRA/FM/06) | Project Leader / Development Engg. | - | -
4. Product & process validation
22 | After tool development, inspect the mould as per Mould Inspection Check Sheet before conduct the trial. Inspection & testing of the jig / fixture / gauge / other equipment as per the requirement. | Manual | After tool development & before trial | Mould Inspection Check Sheet (STPPL/MKD/FM/13) & Jig / fixture / gauges / equipment inspection record. | Project Leader / Development Engg. | - | -
23 | Make the proper arrangement for trial of mould (T0 to Tfinal). Take the trial and keep the samples in product development after trial completion. | Manual | Each time | Trial Requisition Note (STPPL/MKD/FM/06) Trial Report (STPPL/MKD/FM/16) APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. | Inform to customer if trial not taken on the planned date and arrange for the trial at the earliest. | -
24 | Inspect the samples and prepare the SIR. | Manual | After T0 trial | Sample Inspection Report (STPPL/QA/FM/11) | Project Leader / Development Engg. | Inform Tool maker if there is any problem in the mould and get the mould correceted. | -
25 | Send the samples through courier for outside customer and give by hand for local customer. And convey the details to customer. | Manual / Courier | At the time of sample submission | Sample Inspection Report (STPPL/QA/FM/11) Covering Letter Material TC | Project Leader / Development Engg. | - | -
26 | Ensure the customer product approval on the sample submitted. Also ensure that product / process is approved by the customer prior to shipment of the lot. | Manual / Mail / Courier | After sample submission | Customer SIR / Customer written communication. | Project Leader / Development Engg. | If demanded by customer, correction to be done in tool / part. | -
27 | Prepare pilot lot and conduct process capability study, MSA study and packaging evalaution. | Manual | After sample approval | SPC (STPPL/QA/FM/18) & MSA (STPPL/QA/FM/19) | Project Leader / Development Engg. | - | -
28 | Submit the pilot lot to customer & get the feedback. | Manual | After sample approval | PDI report (STPPL/QA/FM/01) | Project Leader / Development Engg. | If demanded by customer, correction to be done in tool / part. | -
29 | Review the design goals & target i.e. productivity, rejection PPM, capability study, RPN etc. | Manual | After pilot lot | MOM | Project Leader / Development Engg. & Project Team Members | - | -
30 | Prepare the PPAP lot and finalize the process documents (PFD, PFMEA, CP, WI, SPPS etc). | Manual | After pilot lot submission | PPAP documents | Project Leader / Development Engg. & Project Team Members | - | -
31 | Submit the PPAP lot to customer & get approved PSW from customer. | Manual | After PPAP lot submission | PSW | Project Leader / Development Engg. | If any issue observed by customer then based on customer feedback initiate corrections | -
32 | Proceed Initial production control activity as per laiddown procedure. (5000 nos. or time duration of 3 months, whichever is later). | Manual | After pilot lot Approval / PSW Approval | SOP- Initial Production control (STPPL/MKD/SOP/16) & Qty. Tracking sheet (STPPL/MKD/FM/12) | Project Leader / Development Engg. & Project Team Members | - | -
33 | Review the manufacturing process design output against manufacturing process design inputs. | Manual | Before project handover | Manufacturing process design output verification (STPPL/MKD/FM/27) | Project Leader / Development Engg. & Project Team Members | If any target not achieved / met, action to be initiate. | -
34 | Project hand over / Termination to be based on customer target achievements along with the all related documents, customer approved sample, Approved waviours if any, jigs, fixtures, gauges, qty. tracking sheet etc. | Manual | At the time of project handover | Project Handover sheet (STPPL / MKD / FM / 15) Qty. Tracking sheet (STPPL/MKD/FM/12) | Project Leader / Development Engg. | - | -
5. Feedback analysis & corrective action
35 | CFT meeting for review of complete project to make summary of things went right, wrong & lesson learnt. The out put for improvements will be used for next project improvements. | Manual | At the time of project handover | Lesson Learnt sheet (STPPL/MKD/FM/20) | Project Leader / Development Engg. & Project Team Members | - | -
APQP Review
36 | Review APQP time plan periodically and initiate the necessary approprite actions on the problem determine with verification and validation. | Manual | Each time of product development | APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. & Project Team Members | - | -
Revision History :
Sr. | Revision in Document |  | Existing No. | Revised No. | Initiated by | Approved by | Prepared by :
1 | Periodic APQP review freqency added, Step sequence revised for PFD, PFMEA, Logo added to Header. |  | 2 | 3 / 23.01.17 | JBR | R.U.Bhutekar
2 | Sr. No. 8 and 9 added for review distribution of engineering specification and review of APQP time plan. |  | 3 / 23.01.17 | 4 / 01.03.2018 | Vaibhav Pawar | R.U.Bhutekar
3 | Added Step No.- 14 & 15, Edited Step No.- 01,12,13,19,20,23,24. Also review & revised steps - Means /device, Frequency, Record /Documents, Responsibility & reaction plan etc.column. |  | 4 / 01.03.2018 | 5 / 11.03.2019 | Vaibhav Pawar | R.U.Bhutekar
4 | Added Step No.- 20 ( SPC,MSA & Training etc.) |  | 5 / 11.03.2019 | 6 / 1.09.2019 | Bhaiya Patil. | R.U.Bhutekar | Approved by :
5 | Step no. 6 revised by capturing the involvement of interested parties in project management. |  | 6 / 1.09.2019 | 7 / 04.01.2021 | Vandana Manchandani | R.U.Bhutekar
6 | Activities organized as per the phases of APQP. |  | 7 / 04.01.2021 | 08 / 28.07.2021 | Umakanti Rajput | R.U.Bhutekar
7 | Added step no. 33 - review of manufacturing process design output. |  | 08 / 28.07.2021 | 09 / 04.09.2021 | Vandana Manchandani | R.U.Bhutekar
8 | IPC / IFM tracking qty. revised to 5000 nos. from 3000 nos. |  | 09 / 04.09.2021 | 10 / 20.11.2021 | Vandana Manchandani | R.U.Bhutekar

## SOP07-APQP rev.11
STPPL | Standard Operating Procedure |  | Purpose : To standardise the process of APQP (Production preparation). |  |  |  | STPPL/MKD/SOP/ 07
| Title : Advanced Product Quality Planning (Production preparation) |  | Scope : Development of new product development. |  |  |  | Rev. No.: 11
Department / Process Owner : Marketing & development | [6 empty] | Rev date: 14.01.2022
Step No. | Operation / Activity Description | Means/Device | Frequency | Record / Document | Responsibility | Reaction Plan | Photograph / Sketch, if applicable
1. Plan & define
1 | Receipt of enquiry from customer in the form of drawing / standard / Sample / other information. Log the enquiry in enquiry register. | Manual / Mail / Telephone / Courrier | Each time of enquiry | Enquiry Register (STPPL/MKD/FM/01) | Officer Marketing / Marketing Process Owner | Response time to new enquiry should be within two working days. | -
2 | Form a CFT for the new product requirement review and conclude on manufacturing feasibility. Intimate to the customer accordingly. | Manual | Each time of enquiry | CFT for APQP (STPPL/MKD/FM/11) & Preliminary feasibility (STPPL/MKD/FM/23) | Project Leader / Development Engg. | - | -
3 | If any concerns raised in the CFT meeting for feasibility commitment then inform to customer about those concerns. | mail,letter. | Each time of product development | CFT for APQP (STPPL/MKD/FM/11) | Project Leader / Development Engg. & Officer Marketing / Marketing Process Owner | - | -
4 | Send the enquiry to tool / fixture / gauge / equipment manufacturer and get the quotation. | Mail, Courier, by hand | Each time of Enquiry | Quotation | Project Leader / Development Engg. / Purchase process owner | - | -
5 | Decide the feasibility on the basis of commercial things and scope for development and mark the comment in enquiry register. | Manual | Each time of Enquiry | Enquiry Register (STPPL/MKD/FM/01) Preliminary / Initial Feasibility Study (STPPL/MKD/FM/23) | Officer Marketing / Marketing Process Owner, Project Leader / Development Engg. & Project Team Members | In case customer does not specify exact requirement, CR will coordinate with customer for the same. | -
6 | If feasible, prepare the quotation of the component and send it to customer. | Manual / Mail / Courrier | Each time of Enquiry | Quotation (STPPL/MKD/FM/08) | Officer Marketing / Marketing Process Owner | If not feasibile, inform to customer. In case customer does not specify exact requirement, CR will coordinate with customer for the same.
7 | Take confirmation from customer in the form of Purchase order, LOI or any written communication. | Manual / Mail / Courrier | Each time of Enquiry | P.O in Customer Format, LOI, Written communication. | Officer Marketing / Marketing Process Owner | - | -
8 | Prepare & refer the APQP responsibility matrix, while carring out the project activities. APQP time plan to be decided by CFT with due consideration of customer requirements, organization objectives etc. Get the approval of top management on the APQP time plan. | After receiving conformation from customer in the form of P.O, LOI or any written communication. | Each time of product development | APQP responsibility matrix (STPPL/MKS/FM/19), APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. | - | -
9 | Form the CFT for APQP and take team feasibility comittment by technical and other required studies. Risk analysis to be done at the time of Feasibility. (Involvement of interested parties like customer, supplier, service provider etc. at the appropriate stages of project management to be considered and to be involved during the appropriate stages of the project management). | Manual | Each time of product development | Team Feasibility Commitment (STPPL/MKD/FM/02) | Project Leader / Development Engg. & Project Team Members | - | -
10 | Identify the special characteristics (product & process). | Manual | Each time of product development | Special characteristics matrix (STPPL/MKD/FM/18) | CFT | - | -
11 | Preparation of micro plan for procurement of tool / fixture / jig / gauge etc. Issue the P.O to tool / fixture / gauge / equipment manufacturer. (tool P.O with detailed annexture) | Manual / Mail / Courrier | Each enquiry as applicable | Supplier P.O | Purchase Process Owner & Project Leader / Development Engg. | - | -
12 | Get the acceptance on micro time plan for tool / fixture / gauge / equipment development from supplier and review the development status periodically. | Manual | As & when required | - | Project Leader / Development Engg. | - | -
13 | Monitor & update micro time plan on weekly basis. Collect activity completion evidences from supplier as per decided time plan. | Manual / Mail / Courrier | Weekly basis, At the time of tool development | APQP Time -Plan chart (STPPL/MKD/FM/03) Mould Development Time Plan (STPPL/MKD/FM/22) | Project Leader / Development Engg. | If any activity not completed as per decided time plan, then take actions plan & target date from suppliers for delays. | -
14 | As per Mould Development Time Plan, demand & receive mould design from tool maker. Discuss the received mould design and cross check the same as per our requirement. If required, mould design discuss with customer also (in case of customer approval). | Manual / Mail / Courrier | At the time of tool development | Mould Development Time Plan (STPPL/MKD/FM/22) 3D CAD Data Tool Design Review Check Sheet (STPPL/MKD/FM/17) | Project Leader & Project Team Members | Inform Tool maker if there is any problem in the mould design and get the mould design corrected. | -
15 | Preparation of preliminary bill of material & process flow diagram. | Manual | Each time of product development | Process flow diagram (STPPL/QA/FM/21) | Project Leader / Development Engg. & Project Team Members | - | -
16 | Review, distribution, and implementation of all customer engineering specifications and related revisions based on customer schedules, as required. | Manual / Mail | Each time of product development | Control of technical specification (STPPL/MKD/FM/25) | Project Leader / Development Engg. | - | -
2. Product design & development (not product design responsible)
17 | Detail review of design requirements related to tool / jig / fixture / gauge / equipment. To identify & record the special characteristics of product & process. | Manual | Each time of product development | Team Feasibility Commitment (STPPL/MKD/FM/02) & Special characteristics matrix (STPPL/MKD/FM/18) | Project Leader / Development Engg. & Project Team Members | - | -
3. Process design & development
18 | After receipt of confirmation from customer, prepare PFD, PFMEA & Control Plan (proto / prelaunch as applicable). | Manual | Each time of product development | PFD (STPPL/QA/FM /21) PFMEA (STPPL/QA/FM/13) Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
19 | Prepare the plan for MSA & process capability study. Conduct the MSA study as per plan. | Manual | Each time of product development | Plan for MSA (STPPL/QA/FM/23) & SPC plan (STPPL/QA/FM/38) | Project Leader / Development Engg. | - | -
20 | Preparation of process instruction (WI) and packaging standard / specification. | Manual | Each time of product development | Product specific WI & packing standard | Project Leader / Development Engg. | - | -
21 | Provide appropriate necessary training to concerned person's related to new product & process. | Manual | As & when required | Training attendance sheet (STPPL/HRA/FM/06) | Project Leader / Development Engg. | - | -
4. Product & process validation
22 | After tool development, inspect the mould as per Mould Inspection Check Sheet before conduct the trial. Inspection & testing of the jig / fixture / gauge / other equipment as per the requirement. | Manual | After tool development & before trial | Mould Inspection Check Sheet (STPPL/MKD/FM/13) & Jig / fixture / gauges / equipment inspection record. | Project Leader / Development Engg. | - | -
23 | Make the proper arrangement for trial of mould (T0 to Tfinal). Take the trial and keep the samples in product development after trial completion. | Manual | Each time | Trial Requisition Note (STPPL/MKD/FM/06) Trial Report (STPPL/MKD/FM/16) APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. | Inform to customer if trial not taken on the planned date and arrange for the trial at the earliest. | -
24 | Inspect the samples and prepare the SIR. | Manual | After T0 trial | Sample Inspection Report (STPPL/QA/FM/11) | Project Leader / Development Engg. | Inform Tool maker if there is any problem in the mould and get the mould correceted. | -
25 | Send the samples through courier for outside customer and give by hand for local customer. And convey the details to customer. | Manual / Courier | At the time of sample submission | Sample Inspection Report (STPPL/QA/FM/11) Covering Letter Material TC | Project Leader / Development Engg. | - | -
26 | Ensure the customer product approval on the sample submitted. Also ensure that product / process is approved by the customer prior to shipment of the lot. | Manual / Mail / Courier | After sample submission | Customer SIR / Customer written communication. | Project Leader / Development Engg. | If demanded by customer, correction to be done in tool / part. | -
27 | Carry out the mass production readiness status prior to going for pilot lot run. | Manual | After sample approval | Mass production readiness check sheet (STPPL/MKD/FM/31) | Project Leader / Development Engg. | If found any gaps, necessary apprpriate action to be initiated prior to pilot lot run.
28 | Prepare pilot lot and conduct process capability study and packaging evalaution. | Manual | After sample approval | SPC (STPPL/QA/FM/18) & MSA (STPPL/QA/FM/19) | Project Leader / Development Engg. | - | -
29 | Submit the pilot lot to customer & get the feedback. | Manual | After sample approval | PDI report (STPPL/QA/FM/01) | Project Leader / Development Engg. | If demanded by customer, correction to be done in tool / part. | -
30 | Review the design goals & target i.e. productivity, rejection PPM, capability study, RPN etc. | Manual | After pilot lot | MOM | Project Leader / Development Engg. & Project Team Members | - | -
31 | Prepare the PPAP lot and finalize the process documents (PFD, PFMEA, CP, WI, SPPS etc). | Manual | After pilot lot submission | PPAP documents | Project Leader / Development Engg. & Project Team Members | - | -
32 | Submit the PPAP lot to customer & get approved PSW from customer. | Manual | After PPAP lot submission | PSW | Project Leader / Development Engg. | If any issue observed by customer then based on customer feedback initiate corrections | -
33 | Proceed Initial production control activity as per laiddown procedure. (5000 nos. or time duration of 3 months, whichever is later). | Manual | After pilot lot Approval / PSW Approval | SOP- Initial Production control (STPPL/MKD/SOP/16) & Qty. Tracking sheet (STPPL/MKD/FM/12) | Project Leader / Development Engg. & Project Team Members | - | -
34 | Review the manufacturing process design output against manufacturing process design inputs. | Manual | Before project handover | Manufacturing process design output verification (STPPL/MKD/FM/27) | Project Leader / Development Engg. & Project Team Members | If any target not achieved / met, action to be initiate. | -
35 | Project hand over / Termination to be based on customer target achievements along with the all related documents, customer approved sample, Approved waviours if any, jigs, fixtures, gauges, qty. tracking sheet etc. | Manual | At the time of project handover | Initial production control tracking sheet (STPPL/MKD/FM/32), Project Handover sheet (STPPL / MKD / FM / 15) Qty. Tracking sheet (STPPL/MKD/FM/12) | Project Leader / Development Engg. | - | -
5. Feedback analysis & corrective action
36 | CFT meeting for review of complete project to make summary of things went right, wrong & lesson learnt. The out put for improvements will be used for next project improvements. | Manual | At the time of project handover | Lesson Learnt sheet (STPPL/MKD/FM/20) | Project Leader / Development Engg. & Project Team Members | - | -
APQP Review
37 | Review APQP time plan periodically and initiate the necessary approprite actions on the problem determine with verification and validation. | Manual | Each time of product development | APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. & Project Team Members | - | -
Revision History :
Sr. | Revision in Document |  | Existing No. | Revised No. | Initiated by | Approved by | Prepared by :
1 | Periodic APQP review freqency added, Step sequence revised for PFD, PFMEA, Logo added to Header. |  | 2 | 3 / 23.01.17 | JBR | R.U.Bhutekar
2 | Sr. No. 8 and 9 added for review distribution of engineering specification and review of APQP time plan. |  | 3 / 23.01.17 | 4 / 01.03.2018 | Vaibhav Pawar | R.U.Bhutekar
3 | Added Step No.- 14 & 15, Edited Step No.- 01,12,13,19,20,23,24. Also review & revised steps - Means /device, Frequency, Record /Documents, Responsibility & reaction plan etc.column. |  | 4 / 01.03.2018 | 5 / 11.03.2019 | Vaibhav Pawar | R.U.Bhutekar
4 | Added Step No.- 20 ( SPC,MSA & Training etc.) |  | 5 / 11.03.2019 | 6 / 1.09.2019 | Bhaiya Patil. | R.U.Bhutekar | Approved by :
5 | Step no. 6 revised by capturing the involvement of interested parties in project management. |  | 6 / 1.09.2019 | 7 / 04.01.2021 | Vandana Manchandani | R.U.Bhutekar
6 | Activities organized as per the phases of APQP. |  | 7 / 04.01.2021 | 08 / 28.07.2021 | Umakanti Rajput | R.U.Bhutekar
7 | Added step no. 33 - review of manufacturing process design output. |  | 08 / 28.07.2021 | 09 / 04.09.2021 | Vandana Manchandani | R.U.Bhutekar
8 | IPC / IFM tracking qty. revised to 5000 nos. from 3000 nos. |  | 09 / 04.09.2021 | 10 / 20.11.2021 | Vandana Manchandani | R.U.Bhutekar
9 | Step no. 08 revised by adding reference of APQP responsibility matrix for preparation of APQP time plan & scope of SOP revised (deleted service development). |  | 10 / 20.11.2021 | 11 / 14.01.2022 | Vandana Manchandani | R.U.Bhutekar

## SOP07-APQP rev.12
STPPL | Standard Operating Procedure |  | Purpose : To standardise the process of APQP (Production preparation). |  |  |  | STPPL/MKD/SOP/ 07
| Title : Advanced Product Quality Planning (Production preparation) |  | Scope : Development of new product development. |  |  |  | Rev. No.: 12
Department / Process Owner : Marketing & development | [6 empty] | Rev date: 07.06.2022
Step No. | Operation / Activity Description | Means/Device | Frequency | Record / Document | Responsibility | Reaction Plan | Photograph / Sketch, if applicable
1. Plan & define
1 | Receipt of enquiry from customer in the form of drawing / standard / Sample / other information. Log the enquiry in enquiry register. | Manual / Mail / Telephone / Courrier | Each time of enquiry | Enquiry Register (STPPL/MKD/FM/01) | Officer Marketing / Marketing Process Owner | Response time to new enquiry should be within two working days. | -
2 | Form a CFT for the new product requirement review and conclude on manufacturing feasibility. Intimate to the customer accordingly. | Manual | Each time of enquiry | CFT for APQP (STPPL/MKD/FM/11) & Preliminary feasibility (STPPL/MKD/FM/23) | Project Leader / Development Engg. | - | -
3 | If any concerns raised in the CFT meeting for feasibility commitment then inform to customer about those concerns. | mail,letter. | Each time of product development | CFT for APQP (STPPL/MKD/FM/11) | Project Leader / Development Engg. & Officer Marketing / Marketing Process Owner | - | -
4 | Send the enquiry to tool / fixture / gauge / equipment manufacturer and get the quotation. | Mail, Courier, by hand | Each time of Enquiry | Quotation | Project Leader / Development Engg. / Purchase process owner | - | -
5 | Decide the feasibility on the basis of commercial things and scope for development and mark the comment in enquiry register. | Manual | Each time of Enquiry | Enquiry Register (STPPL/MKD/FM/01) Preliminary / Initial Feasibility Study (STPPL/MKD/FM/23) | Officer Marketing / Marketing Process Owner, Project Leader / Development Engg. & Project Team Members | In case customer does not specify exact requirement, CR will coordinate with customer for the same. | -
6 | If feasible, prepare the quotation of the component and send it to customer. | Manual / Mail / Courrier | Each time of Enquiry | Quotation (STPPL/MKD/FM/08) | Officer Marketing / Marketing Process Owner | If not feasibile, inform to customer. In case customer does not specify exact requirement, CR will coordinate with customer for the same.
7 | Take confirmation from customer in the form of Purchase order, LOI or any written communication. | Manual / Mail / Courrier | Each time of Enquiry | P.O in Customer Format, LOI, Written communication. | Officer Marketing / Marketing Process Owner | - | -
8 | Prepare & refer the APQP responsibility matrix, while carring out the project activities. APQP time plan to be decided by CFT with due consideration of customer requirements, organization objectives etc. Get the approval of top management on the APQP time plan. | After receiving conformation from customer in the form of P.O, LOI or any written communication. | Each time of product development | APQP responsibility matrix (STPPL/MKS/FM/19), APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. | - | -
9 | Form the CFT for APQP and take team feasibility comittment by technical and other required studies. Risk analysis to be done at the time of Feasibility. (Involvement of interested parties like customer, supplier, service provider etc. at the appropriate stages of project management to be considered and to be involved during the appropriate stages of the project management). | Manual | Each time of product development | Team Feasibility Commitment (STPPL/MKD/FM/02) | Project Leader / Development Engg. & Project Team Members | - | -
10 | Identify the special characteristics (product & process). | Manual | Each time of product development | Special characteristics matrix (STPPL/MKD/FM/18) | CFT | - | -
11 | Preparation of micro plan for procurement of tool / fixture / jig / gauge etc. Issue the P.O to tool / fixture / gauge / equipment manufacturer. (tool P.O with detailed annexture) | Manual / Mail / Courrier | Each enquiry as applicable | Supplier P.O | Purchase Process Owner & Project Leader / Development Engg. | - | -
12 | Get the acceptance on micro time plan for tool / fixture / gauge / equipment development from supplier and review the development status periodically. | Manual | As & when required | - | Project Leader / Development Engg. | - | -
13 | Monitor & update micro time plan on weekly basis. Collect activity completion evidences from supplier as per decided time plan. | Manual / Mail / Courrier | Weekly basis, At the time of tool development | APQP Time -Plan chart (STPPL/MKD/FM/03) Mould Development Time Plan (STPPL/MKD/FM/22) | Project Leader / Development Engg. | If any activity not completed as per decided time plan, then take actions plan & target date from suppliers for delays. | -
14 | As per Mould Development Time Plan, demand & receive mould design from tool maker. Discuss the received mould design and cross check the same as per our requirement. If required, mould design discuss with customer also (in case of customer approval). | Manual / Mail / Courrier | At the time of tool development | Mould Development Time Plan (STPPL/MKD/FM/22) 3D CAD Data Tool Design Review Check Sheet (STPPL/MKD/FM/17) | Project Leader & Project Team Members | Inform Tool maker if there is any problem in the mould design and get the mould design corrected. | -
15 | Preparation of preliminary bill of material & process flow diagram. | Manual | Each time of product development | Process flow diagram (STPPL/QA/FM/21) | Project Leader / Development Engg. & Project Team Members | - | -
16 | Review, distribution, and implementation of all customer engineering specifications and related revisions based on customer schedules, as required. | Manual / Mail | Each time of product development | Control of technical specification (STPPL/MKD/FM/25) | Project Leader / Development Engg. | - | -
17 | Issue of duly reviewed customer requirement and organization requirement to the appropriate supplier as and when applicable. (Engineering specifications, Drawing , Specific requirement and other/ legal applicable requirements if any). Control of technical specification/requirement to the supplier to be reviewed quarterly. | Manual / Mail | Each time of product development and in case of changes in requirement. | Control of technical specification - Supplier (STPPL / PUR / FM / 13) | Project Leader / Development Engg./ Purchase Head | - | -
2. Product design & development (not product design responsible)
18 | Detail review of design requirements related to tool / jig / fixture / gauge / equipment. To identify & record the special characteristics of product & process. | Manual | Each time of product development | Team Feasibility Commitment (STPPL/MKD/FM/02) & Special characteristics matrix (STPPL/MKD/FM/18) | Project Leader / Development Engg. & Project Team Members | - | -
3. Process design & development
19 | After receipt of confirmation from customer, prepare PFD, PFMEA & Control Plan (proto / prelaunch as applicable). | Manual | Each time of product development | PFD (STPPL/QA/FM /21) PFMEA (STPPL/QA/FM/13) Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
20 | Prepare the plan for MSA & process capability study. Conduct the MSA study as per plan. | Manual | Each time of product development | Plan for MSA (STPPL/QA/FM/23) & SPC plan (STPPL/QA/FM/38) | Project Leader / Development Engg. | - | -
21 | Preparation of process instruction (WI) and packaging standard / specification. | Manual | Each time of product development | Product specific WI & packing standard | Project Leader / Development Engg. | - | -
22 | Provide appropriate necessary training to concerned person's related to new product & process. | Manual | As & when required | Training attendance sheet (STPPL/HRA/FM/06) | Project Leader / Development Engg. | - | -
4. Product & process validation
23 | After tool development, inspect the mould as per Mould Inspection Check Sheet before conduct the trial. Inspection & testing of the jig / fixture / gauge / other equipment as per the requirement. | Manual | After tool development & before trial | Mould Inspection Check Sheet (STPPL/MKD/FM/13) & Jig / fixture / gauges / equipment inspection record. | Project Leader / Development Engg. | - | -
24 | Make the proper arrangement for trial of mould (T0 to Tfinal). Take the trial and keep the samples in product development after trial completion. | Manual | Each time | Trial Requisition Note (STPPL/MKD/FM/06) Trial Report (STPPL/MKD/FM/16) APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. | Inform to customer if trial not taken on the planned date and arrange for the trial at the earliest. | -
25 | Inspect the samples and prepare the SIR. | Manual | After T0 trial | Sample Inspection Report (STPPL/QA/FM/11) | Project Leader / Development Engg. | Inform Tool maker if there is any problem in the mould and get the mould correceted. | -
26 | Send the samples through courier for outside customer and give by hand for local customer. And convey the details to customer. | Manual / Courier | At the time of sample submission | Sample Inspection Report (STPPL/QA/FM/11) Covering Letter Material TC | Project Leader / Development Engg. | - | -
27 | Ensure the customer product approval on the sample submitted. Also ensure that product / process is approved by the customer prior to shipment of the lot. | Manual / Mail / Courier | After sample submission | Customer SIR / Customer written communication. | Project Leader / Development Engg. | If demanded by customer, correction to be done in tool / part. | -
28 | Carry out the mass production readiness status prior to going for pilot lot run. | Manual | After sample approval | Mass production readiness check sheet (STPPL/MKD/FM/31) | Project Leader / Development Engg. | If found any gaps, necessary apprpriate action to be initiated prior to pilot lot run.
29 | Prepare pilot lot and conduct process capability study and packaging evalaution. | Manual | After sample approval | SPC (STPPL/QA/FM/18) & MSA (STPPL/QA/FM/19) | Project Leader / Development Engg. | - | -
30 | Submit the pilot lot to customer & get the feedback. | Manual | After sample approval | PDI report (STPPL/QA/FM/01) | Project Leader / Development Engg. | If demanded by customer, correction to be done in tool / part. | -
31 | Review the design goals & target i.e. productivity, rejection PPM, capability study, RPN etc. | Manual | After pilot lot | MOM | Project Leader / Development Engg. & Project Team Members | - | -
32 | Prepare the PPAP lot and finalize the process documents (PFD, PFMEA, CP, WI, SPPS etc). | Manual | After pilot lot submission | PPAP documents | Project Leader / Development Engg. & Project Team Members | - | -
33 | Submit the PPAP lot to customer & get approved PSW from customer. | Manual | After PPAP lot submission | PSW | Project Leader / Development Engg. | If any issue observed by customer then based on customer feedback initiate corrections | -
34 | Proceed Initial production control activity as per laiddown procedure. (5000 nos. or time duration of 3 months, whichever is later). | Manual | After pilot lot Approval / PSW Approval | SOP- Initial Production control (STPPL/MKD/SOP/16) & Qty. Tracking sheet (STPPL/MKD/FM/12) | Project Leader / Development Engg. & Project Team Members | - | -
35 | Review the manufacturing process design output against manufacturing process design inputs. | Manual | Before project handover | Manufacturing process design output verification (STPPL/MKD/FM/27) | Project Leader / Development Engg. & Project Team Members | If any target not achieved / met, action to be initiate. | -
36 | Project hand over / Termination to be based on customer target achievements along with the all related documents, customer approved sample, Approved waviours if any, jigs, fixtures, gauges, qty. tracking sheet etc. During handover process, it is to be ensured that all necessary information and documents are handed over to the appropriate and applicable process owners. like Process product audit report, SPC, deviation approval reports , packing standard, Pre-launch PPAP Documents, BOM, Copy of Drawing, ECN, Approved PSW, Limit/Reference sample, PO from customer, CSR. | Manual | At the time of project handover | Initial production control tracking sheet (STPPL/MKD/FM/32), Project Handover sheet (STPPL / MKD / FM / 15) Qty. Tracking sheet (STPPL/MKD/FM/12) | Project Leader / Development Engg. | - | -
5. Feedback analysis & corrective action
37 | CFT meeting for review of complete project to make summary of things went right, wrong & lesson learnt. The out put for improvements will be used for all next project. | Manual | At the time of project handover | Lesson Learnt sheet (STPPL/MKD/FM/20) | Project Leader / Development Engg. & Project Team Members | - | -
APQP Review
38 | Review APQP time plan periodically and initiate the necessary approprite actions on the problem determine with verification and validation. | Manual | Each time of product development | APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. & Project Team Members | - | -
Revision History :
Sr. | Revision in Document |  | Existing No. | Revised No. | Initiated by | Approved by | Prepared by :
1 | Periodic APQP review freqency added, Step sequence revised for PFD, PFMEA, Logo added to Header. |  | 2 | 3 / 23.01.17 | JBR | R.U.Bhutekar
2 | Sr. No. 8 and 9 added for review distribution of engineering specification and review of APQP time plan. |  | 3 / 23.01.17 | 4 / 01.03.2018 | Vaibhav Pawar | R.U.Bhutekar
3 | Added Step No.- 14 & 15, Edited Step No.- 01,12,13,19,20,23,24. Also review & revised steps - Means /device, Frequency, Record /Documents, Responsibility & reaction plan etc.column. |  | 4 / 01.03.2018 | 5 / 11.03.2019 | Vaibhav Pawar | R.U.Bhutekar
4 | Added Step No.- 20 ( SPC,MSA & Training etc.) |  | 5 / 11.03.2019 | 6 / 1.09.2019 | Bhaiya Patil. | R.U.Bhutekar | Approved by :
5 | Step no. 6 revised by capturing the involvement of interested parties in project management. |  | 6 / 1.09.2019 | 7 / 04.01.2021 | Vandana Manchandani | R.U.Bhutekar
6 | Activities organized as per the phases of APQP. |  | 7 / 04.01.2021 | 08 / 28.07.2021 | Umakanti Rajput | R.U.Bhutekar
7 | Added step no. 33 - review of manufacturing process design output. |  | 08 / 28.07.2021 | 09 / 04.09.2021 | Vandana Manchandani | R.U.Bhutekar
8 | IPC / IFM tracking qty. revised to 5000 nos. from 3000 nos. |  | 09 / 04.09.2021 | 10 / 01.01.2022 | Vandana Manchandani | R.U.Bhutekar
9 | Step no. 08 revised by adding reference of APQP responsibility matrix for preparation of APQP time plan & scope of SOP revised (deleted service development). |  | 10 / 01.01.2022 | 11 / 14.01.2022 | Vandana Manchandani | R.U.Bhutekar
10 | Added step no. 17 in project plan and define stage of the SOP, by adding requirement of control of the technical specification/ requirements to the supplier and Revised step no. 36 for details of project handover . |  | 11 / 14.01.2022 | 12 / 07.06.2022 | Prashant Jena | R.U.Bhutekar

## SOP07-APQP rev.13
STPPL | Standard Operating Procedure |  | Purpose : To standardise the process of APQP (Production preparation). |  |  |  | STPPL/MKD/SOP/ 07
| Title : Advanced Product Quality Planning (Production preparation) |  | Scope : Development of new product development. |  |  |  | Rev. No.: 13
Department / Process Owner : Marketing & development | [6 empty] | Rev date: 04.02.2023
Step No. | Operation / Activity Description | Means/Device | Frequency | Record / Document | Responsibility | Reaction Plan | Photograph / Sketch, if applicable
1. Plan & define
1 | Receipt of enquiry from customer in the form of drawing / standard / Sample / other information. Log the enquiry in enquiry register. | Manual / Mail / Telephone / Courrier | Each time of enquiry | Enquiry Register (STPPL/MKD/FM/01) | Officer Marketing / Marketing Process Owner | Response time to new enquiry should be within two working days. | -
2 | Form a CFT for the new product requirement review and conclude on manufacturing feasibility. Intimate to the customer accordingly. | Manual | Each time of enquiry | CFT for APQP (STPPL/MKD/FM/11) & Preliminary feasibility (STPPL/MKD/FM/23) | Project Leader / Development Engg. | - | -
3 | If any concerns raised in the CFT meeting for feasibility commitment then inform to customer about those concerns. | mail,letter. | Each time of product development | CFT for APQP (STPPL/MKD/FM/11) | Project Leader / Development Engg. & Officer Marketing / Marketing Process Owner | - | -
4 | Send the enquiry to tool / fixture / gauge / equipment manufacturer and get the quotation. | Mail, Courier, by hand | Each time of Enquiry | Quotation | Project Leader / Development Engg. / Purchase process owner | - | -
5 | Decide the feasibility on the basis of commercial things and scope for development and mark the comment in enquiry register. | Manual | Each time of Enquiry | Enquiry Register (STPPL/MKD/FM/01) Preliminary / Initial Feasibility Study (STPPL/MKD/FM/23) | Officer Marketing / Marketing Process Owner, Project Leader / Development Engg. & Project Team Members | In case customer does not specify exact requirement, CR will coordinate with customer for the same. | -
6 | If feasible, prepare the quotation of the component and send it to customer. | Manual / Mail / Courrier | Each time of Enquiry | Quotation (STPPL/MKD/FM/08) | Officer Marketing / Marketing Process Owner | If not feasibile, inform to customer. In case customer does not specify exact requirement, CR will coordinate with customer for the same.
7 | Take confirmation from customer in the form of Purchase order, LOI or any written communication. | Manual / Mail / Courrier | Each time of Enquiry | P.O in Customer Format, LOI, Written communication. | Officer Marketing / Marketing Process Owner | - | -
8 | Prepare & refer the APQP responsibility matrix, while carring out the project activities. APQP time plan to be decided by CFT with due consideration of customer requirements, organization objectives etc. Get the approval of top management on the APQP time plan. | After receiving conformation from customer in the form of P.O, LOI or any written communication. | Each time of product development | APQP responsibility matrix (STPPL/MKS/FM/19), APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. | - | -
9 | Form the CFT for APQP and take team feasibility comittment by technical and other required studies. Risk analysis to be done at the time of Feasibility. (Involvement of interested parties like customer, supplier, service provider etc. at the appropriate stages of project management to be considered and to be involved during the appropriate stages of the project management). | Manual | Each time of product development | Team Feasibility Commitment (STPPL/MKD/FM/02) | Project Leader / Development Engg. & Project Team Members | - | -
10 | Identify the special characteristics (product & process). | Manual | Each time of product development | Special characteristics matrix (STPPL/MKD/FM/18) | CFT | - | -
11 | Preparation of micro plan for procurement of tool / fixture / jig / gauge etc. Issue the P.O to tool / fixture / gauge / equipment manufacturer. (tool P.O with detailed annexture) | Manual / Mail / Courrier | Each enquiry as applicable | Supplier P.O | Purchase Process Owner & Project Leader / Development Engg. | - | -
12 | Get the acceptance on micro time plan for tool / fixture / gauge / equipment development from supplier and review the development status periodically. | Manual | As & when required | - | Project Leader / Development Engg. | - | -
13 | Monitor & update micro time plan on weekly basis. Collect activity completion evidences from supplier as per decided time plan. | Manual / Mail / Courrier | Weekly basis, At the time of tool development | APQP Time -Plan chart (STPPL/MKD/FM/03) Mould Development Time Plan (STPPL/MKD/FM/22) | Project Leader / Development Engg. | If any activity not completed as per decided time plan, then take actions plan & target date from suppliers for delays. | -
14 | As per Mould Development Time Plan, demand & receive mould design from tool maker. Discuss the received mould design and cross check the same as per our requirement. If required, mould design discuss with customer also (in case of customer approval). | Manual / Mail / Courrier | At the time of tool development | Mould Development Time Plan (STPPL/MKD/FM/22) 3D CAD Data Tool Design Review Check Sheet (STPPL/MKD/FM/17) | Project Leader & Project Team Members | Inform Tool maker if there is any problem in the mould design and get the mould design corrected. | -
15 | Preparation of preliminary bill of material & process flow diagram. | Manual | Each time of product development | Process flow diagram (STPPL/QA/FM/21) | Project Leader / Development Engg. & Project Team Members | - | -
16 | Review, distribution, and implementation of all customer engineering specifications and related revisions based on customer schedules, as required. | Manual / Mail | Each time of product development | Control of technical specification (STPPL/MKD/FM/25) | Project Leader / Development Engg. | - | -
17 | Issue of duly reviewed customer requirement and organization requirement to the appropriate supplier as and when applicable. (Engineering specifications, Drawing , Specific requirement and other/ legal applicable requirements if any). Control of technical specification/requirement to the supplier to be reviewed quarterly. | Manual / Mail | Each time of product development and in case of changes in requirement. | Control of technical specification - Supplier (STPPL / PUR / FM / 13) | Project Leader / Development Engg./ Purchase Head | - | -
2. Product design & development (not product design responsible)
18 | Detail review of design requirements related to tool / jig / fixture / gauge / equipment. To identify & record the special characteristics of product & process. | Manual | Each time of product development | Team Feasibility Commitment (STPPL/MKD/FM/02) & Special characteristics matrix (STPPL/MKD/FM/18) | Project Leader / Development Engg. & Project Team Members | - | -
3. Process design & development
19 | After receipt of confirmation from customer, prepare PFD, PFMEA & Control Plan (proto / prelaunch as applicable). | Manual | Each time of product development | PFD (STPPL/QA/FM /21) PFMEA (STPPL/QA/FM/13) Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
20 | Prepare the plan for MSA & process capability study. Conduct the MSA study as per plan. | Manual | Each time of product development | Plan for MSA (STPPL/QA/FM/23) & SPC plan (STPPL/QA/FM/38) | Project Leader / Development Engg. | - | -
21 | Preparation of process instruction (WI) and packaging standard / specification. | Manual | Each time of product development | Product specific WI & packing standard | Project Leader / Development Engg. | - | -
22 | Provide appropriate necessary training to concerned person's related to new product & process. | Manual | As & when required | Training attendance sheet (STPPL/HRA/FM/06) | Project Leader / Development Engg. | - | -
4. Product & process validation
23 | After tool development, inspect the mould as per Mould Inspection Check Sheet before conduct the trial. Inspection & testing of the jig / fixture / gauge / other equipment as per the requirement. | Manual | After tool development & before trial | Mould Inspection Check Sheet (STPPL/MKD/FM/13) & Jig / fixture / gauges / equipment inspection record. | Project Leader / Development Engg. | - | -
24 | Make the proper arrangement for trial of mould (T0 to Tfinal). Take the trial and keep the samples in product development after trial completion. | Manual | Each time | Trial Requisition Note (STPPL/MKD/FM/06) Trial Report (STPPL/MKD/FM/16) APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. | Inform to customer if trial not taken on the planned date and arrange for the trial at the earliest. | -
25 | Inspect the samples and prepare the SIR. | Manual | After T0 trial | Sample Inspection Report (STPPL/QA/FM/11) | Project Leader / Development Engg. | Inform Tool maker if there is any problem in the mould and get the mould correceted. | -
26 | Send the samples through courier for outside customer and give by hand for local customer. And convey the details to customer. | Manual / Courier | At the time of sample submission | Sample Inspection Report (STPPL/QA/FM/11) Covering Letter Material TC | Project Leader / Development Engg. | - | -
27 | Ensure the customer product approval on the sample submitted. Also ensure that product / process is approved by the customer prior to shipment of the lot. | Manual / Mail / Courier | After sample submission | Customer SIR / Customer written communication. | Project Leader / Development Engg. | If demanded by customer, correction to be done in tool / part. | -
28 | Carry out the mass production readiness status prior to going for pilot lot run. | Manual | After sample approval | Mass production readiness check sheet (STPPL/MKD/FM/31) | Project Leader / Development Engg. | If found any gaps, necessary apprpriate action to be initiated prior to pilot lot run.
29 | Prepare pilot lot and conduct process capability study and packaging evalaution. | Manual | After sample approval | SPC (STPPL/QA/FM/18) & MSA (STPPL/QA/FM/19) | Project Leader / Development Engg. | - | -
30 | Submit the pilot lot to customer & get the feedback. | Manual | After sample approval | PDI report (STPPL/QA/FM/01) | Project Leader / Development Engg. | If demanded by customer, correction to be done in tool / part. | -
31 | Review the design goals & target i.e. productivity, rejection PPM, capability study, RPN etc. | Manual | After pilot lot | MOM | Project Leader / Development Engg. & Project Team Members | - | -
32 | Prepare the PPAP lot and process documents by default as per the PPAP level 3 requirement. | Manual | After pilot lot submission | PPAP documents | Project Leader / Development Engg. & Project Team Members | - | -
33 | Submit the PPAP lot to customer & get approved PSW from customer. Either as per PPAP level 3 or PPAP levl 5 document requirement as specified by the customer (Level 3 consider if not specified by customer) In Case of PPAP level 5 requirement only demanded document to be submitted. | Manual | After PPAP lot submission | PSW | Project Leader / Development Engg. | If any issue observed by customer then based on customer feedback initiate corrections | -
34 | Proceed Initial production control activity as per laiddown procedure. (5000 nos. or time duration of 3 months, whichever is later). | Manual | After pilot lot Approval / PSW Approval | SOP- Initial Production control (STPPL/MKD/SOP/16) & Qty. Tracking sheet (STPPL/MKD/FM/12) | Project Leader / Development Engg. & Project Team Members | - | -
35 | Review the manufacturing process design output against manufacturing process design inputs. | Manual | Before project handover | Manufacturing process design output verification (STPPL/MKD/FM/27) | Project Leader / Development Engg. & Project Team Members | If any target not achieved / met, action to be initiate. | -
36 | Project hand over / Termination to be based on customer target achievements along with the all related documents, customer approved sample, Approved waviours if any, jigs, fixtures, gauges, qty. tracking sheet etc. During handover process, it is to be ensured that all necessary information and documents are handed over to the appropriate and applicable process owners. like Process product audit report, SPC, deviation approval reports , packing standard, Pre-launch PPAP Documents, BOM, Copy of Drawing, ECN, Approved PSW, Limit/Reference sample, PO from customer, CSR. | Manual | At the time of project handover | Initial production control tracking sheet (STPPL/MKD/FM/32), Project Handover sheet (STPPL / MKD / FM / 15) Qty. Tracking sheet (STPPL/MKD/FM/12) | Project Leader / Development Engg. | - | -
5. Feedback analysis & corrective action
37 | CFT meeting for review of complete project to make summary of things went right, wrong & lesson learnt. The out put for improvements will be used for all next project. | Manual | At the time of project handover | Lesson Learnt sheet (STPPL/MKD/FM/20) | Project Leader / Development Engg. & Project Team Members | - | -
APQP Review
38 | Review APQP time plan periodically and initiate the necessary approprite actions on the problem determine with verification and validation. | Manual | Each time of product development | APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. & Project Team Members | - | -
Review Date:- 04.02.2023 Review Due on:- 01.02.2024
Revision History :
Sr. | Revision in Document |  | Existing No. | Revised No. | Initiated by | Approved by | Prepared by :
1 | Periodic APQP review freqency added, Step sequence revised for PFD, PFMEA, Logo added to Header. |  | 2 | 3 / 23.01.17 | JBR | R.U.Bhutekar
2 | Sr. No. 8 and 9 added for review distribution of engineering specification and review of APQP time plan. |  | 3 / 23.01.17 | 4 / 01.03.2018 | Vaibhav Pawar | R.U.Bhutekar
3 | Added Step No.- 14 & 15, Edited Step No.- 01,12,13,19,20,23,24. Also review & revised steps - Means /device, Frequency, Record /Documents, Responsibility & reaction plan etc.column. |  | 4 / 01.03.2018 | 5 / 11.03.2019 | Vaibhav Pawar | R.U.Bhutekar
4 | Added Step No.- 20 ( SPC,MSA & Training etc.) |  | 5 / 11.03.2019 | 6 / 1.09.2019 | Bhaiya Patil. | R.U.Bhutekar | Approved by :
5 | Step no. 6 revised by capturing the involvement of interested parties in project management. |  | 6 / 1.09.2019 | 7 / 04.01.2021 | Vandana Manchandani | R.U.Bhutekar
6 | Activities organized as per the phases of APQP. |  | 7 / 04.01.2021 | 08 / 28.07.2021 | Umakanti Rajput | R.U.Bhutekar
7 | Added step no. 33 - review of manufacturing process design output. |  | 08 / 28.07.2021 | 09 / 04.09.2021 | Vandana Manchandani | R.U.Bhutekar
8 | IPC / IFM tracking qty. revised to 5000 nos. from 3000 nos. |  | 09 / 04.09.2021 | 10 / 01.01.2022 | Vandana Manchandani | R.U.Bhutekar
9 | Step no. 08 revised by adding reference of APQP responsibility matrix for preparation of APQP time plan & scope of SOP revised (deleted service development). |  | 10 / 01.01.2022 | 11 / 14.01.2022 | Vandana Manchandani | R.U.Bhutekar
10 | Added step no. 17 in project plan and define stage of the SOP, by adding requirement of control of the technical specification/ requirements to the supplier and Revised step no. 36 for details of project handover . |  | 11 / 14.01.2022 | 12 / 07.06.2022 | Prashant Jena | R.U.Bhutekar
11 | Revised step no. 32 and 33 for PPAP level declaration and document preparation. Review date row added and logo changed |  | 12 / 07.06.2022 | 13 / 04.02.2023 | Umesh Tongire | R.U.Bhutekar

## SOP07-APQP rev.13 (2)
STPPL | Standard Operating Procedure |  | Purpose : To standardise the process of APQP (Production preparation). |  |  |  | STPPL/MKD/SOP/ 07
| Title : Advanced Product Quality Planning (Production preparation) |  | Scope : Development of new product development. |  |  |  | Rev. No.: 13
Department / Process Owner : Marketing & development | [6 empty] | Rev date: 01.02.2024
Step No. | Operation / Activity Description | Means/Device | Frequency | Record / Document | Responsibility | Reaction Plan | Photograph / Sketch, if applicable
1. Plan & define
1 | Receipt of enquiry from customer in the form of drawing / standard / Sample / other information. Log the enquiry in enquiry register. | Manual / Mail / Telephone / Courrier | Each time of enquiry | Enquiry Register (STPPL/MKD/FM/01) | Officer Marketing / Marketing Process Owner | Response time to new enquiry should be within two working days. | -
2 | Form a CFT for the new product requirement review and conclude on manufacturing feasibility. Intimate to the customer accordingly. | Manual | Each time of enquiry | CFT for APQP (STPPL/MKD/FM/11) & Preliminary feasibility (STPPL/MKD/FM/23) | Project Leader / Development Engg. | - | -
3 | If any concerns raised in the CFT meeting for feasibility commitment then inform to customer about those concerns. | mail,letter. | Each time of product development | CFT for APQP (STPPL/MKD/FM/11) | Project Leader / Development Engg. & Officer Marketing / Marketing Process Owner | - | -
4 | Send the enquiry to tool / fixture / gauge / equipment manufacturer and get the quotation. | Mail, Courier, by hand | Each time of Enquiry | Quotation | Project Leader / Development Engg. / Purchase process owner | - | -
5 | Decide the feasibility on the basis of commercial things and scope for development and mark the comment in enquiry register. | Manual | Each time of Enquiry | Enquiry Register (STPPL/MKD/FM/01) Preliminary / Initial Feasibility Study (STPPL/MKD/FM/23) | Officer Marketing / Marketing Process Owner, Project Leader / Development Engg. & Project Team Members | In case customer does not specify exact requirement, CR will coordinate with customer for the same. | -
6 | If feasible, prepare the quotation of the component and send it to customer. | Manual / Mail / Courrier | Each time of Enquiry | Quotation (STPPL/MKD/FM/08) | Officer Marketing / Marketing Process Owner | If not feasibile, inform to customer. In case customer does not specify exact requirement, CR will coordinate with customer for the same.
7 | Take confirmation from customer in the form of Purchase order, LOI or any written communication. | Manual / Mail / Courrier | Each time of Enquiry | P.O in Customer Format, LOI, Written communication. | Officer Marketing / Marketing Process Owner | - | -
8 | Prepare & refer the APQP responsibility matrix, while carring out the project activities. APQP time plan to be decided by CFT with due consideration of customer requirements, organization objectives etc. Get the approval of top management on the APQP time plan. | After receiving conformation from customer in the form of P.O, LOI or any written communication. | Each time of product development | APQP responsibility matrix (STPPL/MKS/FM/19), APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. | - | -
9 | Form the CFT for APQP and take team feasibility comittment by technical and other required studies. Risk analysis to be done at the time of Feasibility. (Involvement of interested parties like customer, supplier, service provider etc. at the appropriate stages of project management to be considered and to be involved during the appropriate stages of the project management). | Manual | Each time of product development | Team Feasibility Commitment (STPPL/MKD/FM/02) | Project Leader / Development Engg. & Project Team Members | - | -
10 | Identify the special characteristics (product & process). | Manual | Each time of product development | Special characteristics matrix (STPPL/MKD/FM/18) | CFT | - | -
11 | Preparation of micro plan for procurement of tool / fixture / jig / gauge etc. Issue the P.O to tool / fixture / gauge / equipment manufacturer. (tool P.O with detailed annexture) | Manual / Mail / Courrier | Each enquiry as applicable | Supplier P.O | Purchase Process Owner & Project Leader / Development Engg. | - | -
12 | Get the acceptance on micro time plan for tool / fixture / gauge / equipment development from supplier and review the development status periodically. | Manual | As & when required | - | Project Leader / Development Engg. | - | -
13 | Monitor & update micro time plan on weekly basis. Collect activity completion evidences from supplier as per decided time plan. | Manual / Mail / Courrier | Weekly basis, At the time of tool development | APQP Time -Plan chart (STPPL/MKD/FM/03) Mould Development Time Plan (STPPL/MKD/FM/22) | Project Leader / Development Engg. | If any activity not completed as per decided time plan, then take actions plan & target date from suppliers for delays. | -
14 | As per Mould Development Time Plan, demand & receive mould design from tool maker. Discuss the received mould design and cross check the same as per our requirement. If required, mould design discuss with customer also (in case of customer approval). | Manual / Mail / Courrier | At the time of tool development | Mould Development Time Plan (STPPL/MKD/FM/22) 3D CAD Data Tool Design Review Check Sheet (STPPL/MKD/FM/17) | Project Leader & Project Team Members | Inform Tool maker if there is any problem in the mould design and get the mould design corrected. | -
15 | Preparation of preliminary bill of material & process flow diagram. | Manual | Each time of product development | Process flow diagram (STPPL/QA/FM/21) | Project Leader / Development Engg. & Project Team Members | - | -
16 | Review, distribution, and implementation of all customer engineering specifications and related revisions based on customer schedules, as required. | Manual / Mail | Each time of product development | Control of technical specification (STPPL/MKD/FM/25) | Project Leader / Development Engg. | - | -
17 | Issue of duly reviewed customer requirement and organization requirement to the appropriate supplier as and when applicable. (Engineering specifications, Drawing , Specific requirement and other/ legal applicable requirements if any). Control of technical specification/requirement to the supplier to be reviewed quarterly. | Manual / Mail | Each time of product development and in case of changes in requirement. | Control of technical specification - Supplier (STPPL / PUR / FM / 13) | Project Leader / Development Engg./ Purchase Head | - | -
2. Product design & development (not product design responsible)
18 | Detail review of design requirements related to tool / jig / fixture / gauge / equipment. To identify & record the special characteristics of product & process. | Manual | Each time of product development | Team Feasibility Commitment (STPPL/MKD/FM/02) & Special characteristics matrix (STPPL/MKD/FM/18) | Project Leader / Development Engg. & Project Team Members | - | -
3. Process design & development
19 | After receipt of confirmation from customer, prepare PFD, PFMEA & Control Plan (proto / prelaunch as applicable). | Manual | Each time of product development | PFD (STPPL/QA/FM /21) PFMEA (STPPL/QA/FM/13) Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
20 | Prepare the plan for MSA & process capability study. Conduct the MSA study as per plan. | Manual | Each time of product development | Plan for MSA (STPPL/QA/FM/23) & SPC plan (STPPL/QA/FM/38) | Project Leader / Development Engg. | - | -
21 | Preparation of process instruction (WI) and packaging standard / specification. | Manual | Each time of product development | Product specific WI & packing standard | Project Leader / Development Engg. | - | -
22 | Provide appropriate necessary training to concerned person's related to new product & process. | Manual | As & when required | Training attendance sheet (STPPL/HRA/FM/06) | Project Leader / Development Engg. | - | -
4. Product & process validation
23 | After tool development, inspect the mould as per Mould Inspection Check Sheet before conduct the trial. Inspection & testing of the jig / fixture / gauge / other equipment as per the requirement. | Manual | After tool development & before trial | Mould Inspection Check Sheet (STPPL/MKD/FM/13) & Jig / fixture / gauges / equipment inspection record. | Project Leader / Development Engg. | - | -
24 | Make the proper arrangement for trial of mould (T0 to Tfinal). Take the trial and keep the samples in product development after trial completion. | Manual | Each time | Trial Requisition Note (STPPL/MKD/FM/06) Trial Report (STPPL/MKD/FM/16) APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. | Inform to customer if trial not taken on the planned date and arrange for the trial at the earliest. | -
25 | Inspect the samples and prepare the SIR. | Manual | After T0 trial | Sample Inspection Report (STPPL/QA/FM/11) | Project Leader / Development Engg. | Inform Tool maker if there is any problem in the mould and get the mould correceted. | -
26 | Send the samples through courier for outside customer and give by hand for local customer. And convey the details to customer. | Manual / Courier | At the time of sample submission | Sample Inspection Report (STPPL/QA/FM/11) Covering Letter Material TC | Project Leader / Development Engg. | - | -
27 | Ensure the customer product approval on the sample submitted. Also ensure that product / process is approved by the customer prior to shipment of the lot. | Manual / Mail / Courier | After sample submission | Customer SIR / Customer written communication. | Project Leader / Development Engg. | If demanded by customer, correction to be done in tool / part. | -
28 | Carry out the mass production readiness status prior to going for pilot lot run. | Manual | After sample approval | Mass production readiness check sheet (STPPL/MKD/FM/31) | Project Leader / Development Engg. | If found any gaps, necessary apprpriate action to be initiated prior to pilot lot run.
29 | Prepare pilot lot and conduct process capability study and packaging evalaution. | Manual | After sample approval | SPC (STPPL/QA/FM/18) & MSA (STPPL/QA/FM/19) | Project Leader / Development Engg. | - | -
30 | Submit the pilot lot to customer & get the feedback. | Manual | After sample approval | PDI report (STPPL/QA/FM/01) | Project Leader / Development Engg. | If demanded by customer, correction to be done in tool / part. | -
31 | Review the design goals & target i.e. productivity, rejection PPM, capability study, RPN etc. | Manual | After pilot lot | MOM | Project Leader / Development Engg. & Project Team Members | - | -
32 | Prepare the PPAP lot and process documents by default as per the PPAP level 3 requirement. | Manual | After pilot lot submission | PPAP documents | Project Leader / Development Engg. & Project Team Members | - | -
33 | Submit the PPAP lot to customer & get approved PSW from customer. Either as per PPAP level 3 or PPAP levl 5 document requirement as specified by the customer (Level 3 consider if not specified by customer) In Case of PPAP level 5 requirement only demanded document to be submitted. | Manual | After PPAP lot submission | PSW | Project Leader / Development Engg. | If any issue observed by customer then based on customer feedback initiate corrections | -
34 | Proceed Initial production control activity as per laiddown procedure. (5000 nos. or time duration of 3 months, whichever is later). | Manual | After pilot lot Approval / PSW Approval | SOP- Initial Production control (STPPL/MKD/SOP/16) & Qty. Tracking sheet (STPPL/MKD/FM/12) | Project Leader / Development Engg. & Project Team Members | - | -
35 | Review the manufacturing process design output against manufacturing process design inputs. | Manual | Before project handover | Manufacturing process design output verification (STPPL/MKD/FM/27) | Project Leader / Development Engg. & Project Team Members | If any target not achieved / met, action to be initiate. | -
36 | Project hand over / Termination to be based on customer target achievements along with the all related documents, customer approved sample, Approved waviours if any, jigs, fixtures, gauges, qty. tracking sheet etc. During handover process, it is to be ensured that all necessary information and documents are handed over to the appropriate and applicable process owners. like Process product audit report, SPC, deviation approval reports , packing standard, Pre-launch PPAP Documents, BOM, Copy of Drawing, ECN, Approved PSW, Limit/Reference sample, PO from customer, CSR. | Manual | At the time of project handover | Initial production control tracking sheet (STPPL/MKD/FM/32), Project Handover sheet (STPPL / MKD / FM / 15) Qty. Tracking sheet (STPPL/MKD/FM/12) | Project Leader / Development Engg. | - | -
5. Feedback analysis & corrective action
37 | CFT meeting for review of complete project to make summary of things went right, wrong & lesson learnt. The out put for improvements will be used for all next project. | Manual | At the time of project handover | Lesson Learnt sheet (STPPL/MKD/FM/20) | Project Leader / Development Engg. & Project Team Members | - | -
APQP Review
38 | Review APQP time plan periodically and initiate the necessary approprite actions on the problem determine with verification and validation. | Manual | Each time of product development | APQP Time -Plan chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. & Project Team Members | - | -
Review Date:- 01.02.2024 Review Due on:- 01.02.2025
Revision History :
Sr. | Revision in Document |  | Existing No. | Revised No. | Initiated by | Approved by | Prepared by :
1 | Periodic APQP review freqency added, Step sequence revised for PFD, PFMEA, Logo added to Header. |  | 2 | 3 / 23.01.17 | JBR | R.U.Bhutekar
2 | Sr. No. 8 and 9 added for review distribution of engineering specification and review of APQP time plan. |  | 3 / 23.01.17 | 4 / 01.03.2018 | Vaibhav Pawar | R.U.Bhutekar
3 | Added Step No.- 14 & 15, Edited Step No.- 01,12,13,19,20,23,24. Also review & revised steps - Means /device, Frequency, Record /Documents, Responsibility & reaction plan etc.column. |  | 4 / 01.03.2018 | 5 / 11.03.2019 | Vaibhav Pawar | R.U.Bhutekar
4 | Added Step No.- 20 ( SPC,MSA & Training etc.) |  | 5 / 11.03.2019 | 6 / 1.09.2019 | Bhaiya Patil. | R.U.Bhutekar | Approved by :
5 | Step no. 6 revised by capturing the involvement of interested parties in project management. |  | 6 / 1.09.2019 | 7 / 04.01.2021 | Vandana Manchandani | R.U.Bhutekar
6 | Activities organized as per the phases of APQP. |  | 7 / 04.01.2021 | 08 / 28.07.2021 | Umakanti Rajput | R.U.Bhutekar
7 | Added step no. 33 - review of manufacturing process design output. |  | 08 / 28.07.2021 | 09 / 04.09.2021 | Vandana Manchandani | R.U.Bhutekar
8 | IPC / IFM tracking qty. revised to 5000 nos. from 3000 nos. |  | 09 / 04.09.2021 | 10 / 01.01.2022 | Vandana Manchandani | R.U.Bhutekar
9 | Step no. 08 revised by adding reference of APQP responsibility matrix for preparation of APQP time plan & scope of SOP revised (deleted service development). |  | 10 / 01.01.2022 | 11 / 14.01.2022 | Vandana Manchandani | R.U.Bhutekar
10 | Added step no. 17 in project plan and define stage of the SOP, by adding requirement of control of the technical specification/ requirements to the supplier and Revised step no. 36 for details of project handover . |  | 11 / 14.01.2022 | 12 / 07.06.2022 | Prashant Jena | R.U.Bhutekar
11 | Revised step no. 32 and 33 for PPAP level declaration and document preparation. Review date row added and logo changed |  | 12 / 07.06.2022 | 13 / 04.02.2023 | Umesh Tongire | R.U.Bhutekar
12 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  | 13 / 04.02.2023 | 13 / 01.02.2024 | A. Deshmukh | R.U.Bhutekar