## Rev.09 (3)
STPPL | Standard Operating Procedure |  | Purpose : To standardise the procedure for PFMEA. |  |  |  | STPPL/MKD/SOP/ 15
| Title : Process Failure Mode Effect Analysis. |  | Scope : Applicable for all new product & process development and changes in product and processes. |  |  |  | Rev. No.: 09
Department / Process Owner : Marketing & Development. | [6 empty] | Rev date: 01.02.2025
Step No. | Operation / Activity Description | Means / Device | Frequency | Record / Document | Responsibility | Reaction Plan | Photograph / Sketch, if applicable
1 | Form a cross functional team (CFT) and conduct the meeting. (Involvement of interested parties like customer, supplier, service provider etc. in the PFMEA activity if found necessary & appropriate). | Manual | Each time | - | Project Leader / Development Engg. & Project Team Members | - | -
2 | Refer past quality data as input for preparation FMEA like lesson learnt, customer complaints, in-house rejection, development issues, supplier rejection / issues, warrenty / field failures etc. Minimum last six months back up data to be refered while preparing the FMEA / failure mode analysis. | Manual | Each time | Lesson learnt sheet (STPPL/MKD/FM/20) | Project Leader / Development Engg. & Project Team Members | - | -
3 | Complete the header on the FMEA Form worksheet: Item, process responsibility, FMEA number, model year / program, key date, FMEA rev. no, rev. date, core team and prepared by. Modify these headings as needed. | Manual | Each time | PFMEA sheet (STPPL/QA/FM/13) | Project Leader / Development Engg. & Project Team Members | - | -
4 | Describe the product / process and its function requirements in process step, function and requirement cloumn. An understanding of the product or process under consideration is important to have clearly vision on development. | Manual | Each time | PFD Sheet (STPPL/QA/FM/21), PFMEA sheet (STPPL/QA/FM/13) | Project Leader / Development Engg. & Project Team Members | - | -
5 | Identify Failure Modes. A failure mode is defined as the manner in which a component, subsystem, system, process, etc. could potentially fail to meet the design intent. Past lesson learnts of similar running components to be considered during FMEA preparation. | Manual | Each time | PFMEA sheet (STPPL/QA/FM/13), Lesson learnt sheet (STPPL/QA/FM/29) | Project Leader / Development Engg. & Project Team Members | - | -
6 | Failure mode should be listed for function of each component or process & sub process . At this point, the failure mode should be identified, whether or not the failure is likely to occure. Looking at similar products or processes and the failures, that have been documented for it is an excellent starting point.For Inputs,use Lesson learnt ,PFD,PFMEA,Control Plan for similar products or process. | Manual | Each time | PFMEA sheet (STPPL/QA/FM/13) Lesson learnt sheet (STPPL/QA/FM/29) | Project Leader / Development Engg. & Project Team Members | - | -
7 | Describe the effects of these failure modes. For each failure mode identified, the engineer should determine what the ultimate effect will be. A failure effect is defined as the result of a failure mode on the function of the product/process as perceived by the customer. | Manual | Each time | PFMEA sheet (STPPL/QA/FM/13) | Project Leader / Development Engg. & Project Team Members | - | -
8 | Establish a numerical ranking for the severity of the effect. Refer annexure 1 for severity ranking. For Severity ranking is >/= 7 then it should have reaction plan to get it down as per guidelines provided by AIAG in FMEA 4th Edition. | Manual | Each time | PFMEA sheet (STPPL/QA/FM/13) Severity Ranking Table AIAG FMEA Latest Manual | Project Leader / Development Engg. & Project Team Members | - | -
9 | Identify special characteristics, including those determined by the customer and the risk analysis performed by our CFT. Convert all identified special characteristics into special symbol or notation, as defined in special characteristics matrix and same matrix to be shared to customer, if required. Ensure the co-herance of the document i.e. step no.,special charcateristics details etc.in line with the part PFD. | Manual | Each time | Special characteristics matrix (STPPL/MKD/FM/18) | Project Leader / Development Engg. & Project Team Members | - | -
10 | All identified special characetristics with special symbol / notation to be cascaded through all related documents uniquely. (PFD, FMEA, Control plan, Work instruction, Specification sheets, drawing etc). | Manual | Each time | Special characteristics matrix (STPPL/MKD/FM/18), PFD Sheet (STPPL/QA/FM/21), PFMEA sheet (STPPL/QA/FM/13) | Project Leader / Development Engg. & Project Team Members | - | -
11 | Identify the causes for each failure mode. A failure cause is defined as a design weakness that may result in a failure. The potential causes for each failure mode should be identified and documented. | Manual | Each time | PFMEA sheet (STPPL/QA/FM/13) | Project Leader / Development Engg. & Project Team Members | - | -
12 | Enter the probability factor, a numerical weight should be assigned to each cause which that indicates, how likely that cause may occure. (probability of the cause occuring). Based on the Current Controls, consider the likelihood of occurrence using the table (annexure 2 ) for guidance provided by AIAG in FMEA 4th revision. | Manual | Each time | PFMEA sheet (STPPL/QA/FM/13) Occurance Ranking Table AIAG FMEA Latest Manual | Project Leader / Development Engg. & Project Team Members | - | -
13 | Identify Current Controls (design or process). Current Controls (design or process) are the mechanisms, that prevent the cause of the failure mode from occurring or which detect the failure before it reaches to the Customer. The engineer should now identify testing, analysis, monitoring, and other techniques that can or have been used on the same or similar products/processes to detect the failures. | Manual | Each time | PFMEA sheet (STPPL/QA/FM/13) | Project Leader / Development Engg. & Project Team Members | - | -
14 | Determine the likelihood of detection. Detection is an assessment of the likelihood that, the current controls (design and process) will detect the cause of the Failure Mode or the Failure Mode itself, thus preventing it from reaching it to the Customer. Based on the Current Controls, consider the likelihood of Detection using the table (annexure 3) for guidance provided by AIAG in FMEA 4th revision. | Manual | Each time | PFMEA sheet (STPPL/QA/FM/13) Detection Ranking Table AIAG FMEA Latest Manual | Project Leader / Development Engg. & Project Team Members | - | -
15 | Review Risk Priority Numbers (RPN). The Risk Priority Number is a mathematical product of the numerical Severity, Occurrence, and Detection ratings: RPN = (Severity) x (Occurrence) x (Detection) The RPN is used to prioritize items than require additional quality planning or action. In case of following conditions then it should have reaction plan to get it down. A.Severity X Occurrence >36 B.Top three RPN values | Manual | Each time | PFMEA sheet (STPPL/QA/FM/13) | Project Leader / Development Engg. & Project Team Members | - | -
16 | Recommended Actions should be taken as per guidelines provided by AIAG in FMEA 4th revision or as per customer requirement. In general, prevention actions (i.e., reducing the occurrence) are preferable to detection actions.The intent of any recommended action is to reduce rankings in the following order: severity, occurrence, and detection. | Manual | Each time | PFMEA sheet (STPPL/QA/FM/13) | Project Leader / Development Engg. & Project Team Members | - | -
17 | Responsibility & Target Completion Date - Enter the name of the individual and organization responsible for completing each recommended action including the target completion date. The process -responsible engineer / team leader is responsible for ensuring that, all actions recommended have been implemented or adequately addressed. | Manual | Each time | PFMEA sheet (STPPL/QA/FM/13) | Project Leader / Development Engg. & Project Team Members | - | -
18 | Action Results This section identifies the results of any completed actions and its effect on Severity, Occurrence & Detection rankings and R.P.N. | Manual | Each time | PFMEA sheet (STPPL/QA/FM/13) | Project Leader / Development Engg. & Project Team Members | - | -
19 | Actions Taken and Completion Date After the action has been implemented, enter a brief description of the action taken and actual completion date, if required. | Manual | Each time | PFMEA sheet (STPPL/QA/FM/13) | Project Leader / Development Engg. & Project Team Members | - | -
20 | FMEA should be reviewed & revised (if applicable), during following cases - A. For Initial Production Control B. For any change in product or process design change and update. C. For any customer complaint D. For any Warranty Failure E. For Increase in Inprocess rejection PPM | Manual | Each time | PFMEA sheet (STPPL/QA/FM/13) | Project Leader / Development Engg. / Q.A Process Owner & Project Team Members | - | -
21 | Review of FMEA in case of shipped nonconforming product to the customer, any change occurs affecting product, manufacturing process, measurement, logistics, supply sources, production volume changes, or risk analysis, customer complaint and implementation of associated corrective action, found non- confirming product, unstable process, set frequency based on risk analysis and regular reviews once in a year. If required by the customer, obtain customer approval after review or revision of FMEA. | Manual | Each time of changes | PFMEA sheet (STPPL/QA/FM/13), FMEA / PPAP review plan (STPPL/QA/FM/24) | Development Head and QA Head | - | -
22 | Prepare the FMEA as per new AIAG+VDA FMEA edition 1 guidelines, on special customer requirement. | Manual | As & when required | FMEA manual (AIAG+VDA) PFMEA sheet (STPPL/MKD/FM/29) | Project Leader / Development Engg. / Q.A Process Owner & Project Team Members | - | -
Review Date:- 01.02.2025 Review Due on:- 01.02.2026
Revision History :
Sr.No | Revision in Document |  | Existing No. | Revised No. | Initiated by | Approved by | Prepared by :
1 | Company Logo Added in Header ,Sr. No 5 Modified for additional Inputs, Sr.No.12 Modified for RPN values & reaction plan, Ranking Table point for Severity, Occurrence & Detection added. Sr.No. 17 Added for review frequency, Added Lesson Learnt Sheet in Record column. |  | 0 | 1 | JBR | RUB
2 | Step No. 26 added for review of the control plan. |  | 1 | 2 / 01.03.2018 | Vaibhav Pawar | R.U.Bhutekar
3 | Review & revised steps for - Record /Documents & Responsibility column. |  | 2 / 01.03.2018 | 3 / 11.03.2019 | Vaibhav Pawar | R.U.Bhutekar
4 | Review & revised step no. 1 for cross functional team members (involvement of interested parties). |  | 03 / 11.03.2019 | 04 / 04.01.2021 | Vandana Manchandani | R.U.Bhutekar | Approved by :
5 | Revised SOP by addition of step no. 08 & 09 related to special characteristics, conversion of special characteristics and converted symbol cascaded through all related documented information. |  | 04 / 04.01.2021 | 05 / 16.09.2021 | Umakanti Rajput | R.U.Bhutekar
6 | Revised SOP by addition of step no. 21 related to prepration of FMEA as per AIAG+VDA FMEA edition 1 guidelines, on special customer requirement. |  | 05 / 16.09.2021 | 06 / 20.11.2021 | Vandana Manchandani | R.U.Bhutekar
4 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  | 06 / 20.11.2021 | 06 / 01.01.2022 | Vandana Manchandani | R.U.Bhutekar.
7 | Step no. 02 added consideration of inputs to be taken for preparation of FMEA. And step no. 21 revised by adding FMEA / PPAP review plan format no. in record / doc. column. Also added the rule of refering minimum last six months data in step no. 02. |  | 06 / 01.01.2022 | 07 / 14.01.2022 | Vandana Manchandani | R.U.Bhutekar
8 | Review date row added and logo changed |  | 07 / 14.01.2022 | 08 / 04.02.2023 | C. Khose | R.U.Bhutekar
9 | Revised step no. 09 by adding co-herance of document i.e. PFD & PFMEA & CP matching.(step no., special charcteristics etc.) |  | 08 / 04.02.2023 | 09/ 07.10.2023 | Mr. Ashutosh Upreti. | R.U.Bhutekar
10 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  | 09/ 07.10.2023 | 09/ 01.02.2024 | Abhijit Deshmukh | R.U.Bhutekar
11 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  | 09/ 01.02.2024 | 09/ 01.02.2025 | Abhijit Deshmukh | R.U.Bhutekar