## Rev 04 (3)
STPPL | Standard Operating Procedure |  | Purpose : To standardise the process for project handover |  |  |  | STPPL / MKD / SOP / 06
| Title : Project Handover |  | Scope : Project handover in case of new product development & fulfilling the requirement of initial production control satisfactory. |  |  |  | Rev. No. :04
Department / Process Owner : Marketing and Development | [6 empty] | Rev. Date : 01.02.2025
Step No. | Operation / Activity Description | Means/Device | Frequency | Record / Document | Responsibility | Reaction Plan | Photograph / Sketch, if applicable
1 | After termination of the initial production control (IPC / IFM) by the person authorized (reference - initial production control - STPPL/MKD/SOP/16). Take the limit samples from customer. | Manual | At the time of project handover | - | Project Leader / Development Engg. | If customer approved sample is not received then take the limit sample from MKD head | -
2 | Collect all the details of the project and prepare the bill of material. | Manual | At the time of project handover | Bill of Material (STPPL/PUR/FM/07) | Project Leader / Development Engg. | - | -
3 | Take the standard process parameter sheet and Process flow diagram. | Manual | At the time of project handover | Standard process parameter sheet (STPPL/MLD/FM/01) Process Flow Diagram (STPPL/QA/FM/21) | Project Leader / Development Engg. | - | -
4 | Take the details/photographs of packing arrangement if required | Manual | At the time of project handover | - | Project Leader / Development Engg. | - | -
5 | Take the recent drawing copy with latest modification and engineering change note.if any. | Manual | At the time of project handover | Drawing Copy | Project Leader / Development Engg. | - | -
6 | Take our Sample Inspection Report (SIR) and Customer Sample Inspection Report (SIR) copy. | Manual | At the time of project handover | Sample Inspection Report (STPPL/QA/FM/11) | Project Leader / Development Engg. | - | -
7 | Take the copy of Purchase Order from customer. | Manual | At the time of project handover | P.O. from customer | Project Leader / Development Engg. | - | -
8 | Prepare FMEA and pre-launch control plan. | Manual | At the time of project handover | PFMEA (STPPL/QA/FM/13) | Project Leader / Development Engg. | - | -
9 | Prepare the bunch of documents as per the Index . | Manual | At the time of project handover | - | Project Leader / Development Engg. | - | -
10 | Take the print out of Project handover sheet. | Manual | At the time of project handover | Project Handover sheet (STPPL/MKD/FM/15) | Project Leader / Development Engg. | - | -
11 | Take the approval sign on each document from authorized person. | Manual | At the time of project handover | Project Handover sheet (STPPL/MKD/FM/15) | Project Leader / Development Engg. | - | -
12 | Make the distribution of the documents departmentwise. | Manual | At the time of project handover | Project Handover sheet (STPPL/MKD/FM/15) | Project Leader / Development Engg. | - | -
13 | Handover the limit sample To Q.A department. | Manual | At the time of project handover | Project Handover sheet (STPPL/MKD/FM/15) | Project Leader / Development Engg. | - | -
14 | Handover the bunch of the documents, department wise and take the sign of the related person . | Manual | At the time of project handover | Project Handover sheet (STPPL/MKD/FM/15) | Project Leader / Development Engg. | - | -
Review Date:- 04.02.2024 Review Due on:- 01.02.2026
Revision History :
Sr. | Revision in Document |  | Existing No. | Revised No. | Initiated by | Approved by | Prepared by :
1 | Logo Added |  | 0 | 1 | JBR | RUB
2 | Modified Step No.- 06,13,14. Also review & revised steps - Record /Documents, Responsibility & Reaction plan etc.column. |  | 1 / 23.01.2017 | 2 / 11.03.2019 | Vaibhav Pawar | R.U.Bhutekar | Approved by :
3 | Added termination of initial production control in the step no. 01. |  | 2 / 11.03.2019 | 3 / 20.11.2021 | Vandana M. | R.U.Bhutekar
5 | Review date row added and logo changed |  | 03 / 20.11.2021 | 04/ 04.02.2023 | C.khose | R.U.Bhutekar
6 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  | 04/ 04.02.2023 | 04/ 01.02.2024 | A. Deshmukh | R.U.Bhutekar
7 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  | 04/ 01.02.2024 | 04/ 01.02.2025 | A. Deshmukh | R.U.Bhutekar