## Rev 02 (3)
STPPL | Standard Operating Procedure |  | Purpose : To standardise the process of new product development in case of tool / mould supplied by the customer. |  |  |  | STPPL/MKD/SOP/18
Rev. No.: 02
| Title : New product development with customer tooling |  | Scope : Development of new product with customer tooling. |  |  |  | Rev. Date:01.02.2025
Department : Marketing & development. | [6 empty] | Page 01 of 03
Step No. | Operation / Activity Description | Means/Device | When? | Record / Document | Responsibility | Reaction Plan | Photograph / Sketch, if applicable
1 | Receive the enquiry from the customer | Manual / Mail / Telephone / Courrier | Each time of enquiry | Enquiry Register (STPPL/MKD/FM/01) | Marketing process owner | Response time to new enquiry should be within two working days. | -
2 | Receipt of drawing / sample / specification / Model etc. | Manual / Mail / Courrier | Each time of enquiry | Enquiry Register (STPPL/MKD/FM/01) | Marketing process owner | - | -
3 | Initial feasibility study & preperation of feasibility study report. | Manual | Each time of enquiry | Preliminary Feasibility Format (STPPL/MKD/FM/23) | Lead by MKD process owner & supported by CFT | If not feasibile , inform to customer. In case customer does not specify exact requirement, CR will coordinate with customer for the same. | -
4 | To prepare quote the based on feasibility study & detail detailed working | Manual | Each time of enquiry | Quotation (STPPL/MKD/FM/08) | Marketing process owner | - | -
5 | Customer P.O / LOI / written communication etc. | Manual | Each time of enquiry | P.O in Customer Format, LOI, Written communication. | Marketing process owner | - | - | .
6 | CFT meeting on feasibility with available input of drawing / sample / CSR / material / quantity / quality requirements / agreement of inspection / jig fixtures / part past history / similar product with us / last complaints / issues in the part / master sample / limit sample / last piece / mould history card etc. | Manual | After receiving conformation from customer in the form of P.O, LOI or any written communication. | Team Feasibility Commitment (STPPL/MKD/FM/02) | Lead by Development process owner & supported by CFT | - | -
7 | If any concerns raised in the CFT meeting for feasibility commitment then inform to customer about those concerns. | Mail,letter. | After Team Feasibility Commitment | Team Feasibility Commitment (STPPL/MKD/FM/02) | Marketing & Development process owner | - | -
8 | Preperation of SC ,CC matrix, PFD, PFMEA, pre-launch control plan, Inspection checksheet FPA ,Inprocess & final inspection criteria / standard, work instruction, packing standard etc. | Manual | After Team Feasibility Commitment | Special Characteristic Matrix (STPPL/MKD/FM/18) PFD (STPPL/QA/FM /21) PFMEA (STPPL/QA/FM/13) Control Plan (STPPL/QA/FM/15) Inspection Standard Checksheet (STPPL/QA/FM/05) List of Packing Standard (STPPL/STR/LT/05) | Lead by Quality Assurance process owner & supported by CFT | - | -
9 | Receipt of mould & mould inspection as per check list. Mould physical verification. | Manual | After receipt the mould & before trial | Mould Inspection Check Sheet (STPPL/MKD/FM/13) | Mould Maintenance Process Owner | - | -
10 | Arrangement for mould trial - a.Trial request. b. Trial report. c. Set-up approval (FPA) d. SPPS freezing e. Sample inspection report f. Performance evaluation - rejection / capability / ease of operation. | Manual | After receipt the mould & during trial | Trial Requisition Note (STPPL/MKD/FM/06) Trial Report (STPPL/MKD/FM/16) First / Last Piece Inspection Report (STPPL/QA/FM/46) Standard Process Parameter Sheet (STPPL/MLD/FM/01) Sample Inspection Report (STPPL/QA/FM/11) | a.Marketing process owner b.Production process owner c.Quality Assurance process owner d.Production & Maint. process owner e.Quality Assurance process owner f. Lead by production & supported by CFT | - | -
11 | Sample submission & customer approval including any deviation. Customer / joint inspection and sample approval in case of trial in the presence of customer representative. | Manual | After trial | Sample Inspection Report (STPPL/QA/FM/11) Customer Approval | Lead by Marketing process owner for customer approval & Supported by Quality Assurance process owner for sample submission | In case of deviation MKD process owner will coordinate with customer for written approval | -
12 | To conduct PPAP run with reference to AIAG PPAP latest manual. | Manual | Each time | PPAP all documents PSW (STPPL/QA/FM/17) PPAP AIAG latest reference manual | Lead by Production & Maint. process owner for production run & Supported by Quality Assurance process owner for PPAP documents | - | -
13 | Inspection of PPAP lot with PPAP document and approval of PSW. | Manual | Each time | PPAP all document PSW (STPPL/QA/FM/17) | Quality Assurance process owner | - | -
14 | Submission of pilot lot with PPAP document & approval on PSW. | Manual | Each time | PSW (STPPL/QA/FM/17) | Lead by Quality Assuarance process owner for submission of pilot lot & Supported by Marketing process owner for customer PSW approval
15 | CFT meeting on PPAP lot output. | Manual | After PPAP lot production | Cross Functional Team For APQP (STPPL/MKD/FM/11) | Lead by Marketing process owner & Supported by Quality Assurance process owner & CFT | - | -
16 | To revise the PPAP from pre-launch to production. | Manual | After PPAP lot production | PPAP all document PSW (STPPL/QA/FM/17) | Quality Assurance process owner | - | -
17 | Monitor next three lots before commercial production as per the common / QMS system regular. On successful delivery and acceptance of product at customer end, the project will be handed over to production for serial production. | Manual | Each time | Quantity Tracking Sheet (STPPL/MKD/FM/12) & Project handover sheet (STPPL/MKD/FM/15) | Lead by Quality Assurance process owner & Supported by CFT | - | -
18 | To control the changes in 4M and ensure proper ECN. | Manual | Each time of changes | SOP of 4M Change (STPPL/QA/SOP/17) Modification Review Check List (STPPL/MKD/FM/14) | For Customer approval Marketing process owner & for changes Mould Maintenance process owner | - | -
19 | In case of the customer demands manufacturing of tool along with the process design & development. The mould manufacturing will be carried out by STPPL Aurangabad MKD department & on sample approval the mould will handed over to STPL PN plant. | Manual | As & when required | Sample Inspection Report (STPPL/QA/FM/11) Customer Approval & Enquiry register (STPPL/MKD/FM/01) | Marketing process owner | - | -
Review Date:- 01.02.2025 Review Due on:- 01.02.2026
Revision History :
Sr. | Revision in Document |  | Existing No. | Revised No. | Initiated by | Approved by | Prepared by :
1 | Added step no. 19 and step no. 17 revised for addition of project handover. |  | 0 / 06.04.2019 | 01 / 01.01.2021 | Sunder Singh | R.U. Bhutekar
2 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  | 01 / 01.01.2021 | 01 / 01.01.2022 | Sonusingh Rathod | R.U. Bhutekar | Approved by :
3 | Review date row added and logo changed |  | 01 / 01.01.2022 | 02 / 04.02.2023 | C. Khose | R.U.Bhutekar
4 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  | 02 / 04.02.2023 | 02 / 01.02.2024 | A. Deshmukh | R.U.Bhutekar
5 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  | 02 / 01.02.2024 | 02 / 01.02.2025 | A. Deshmukh | R.U.Bhutekar