## Rev 05 (2)
STPPL | Standard Operating Procedure |  | Purpose : To define responsibility & authorities to identify & implement the continual improvement projects to take proactive steps to continually improve the effectiveness of the QMS . |  |  |  | STPPL / MR / SOP / 07
Rev. No. : 05
| Title : Standard Operating Procedure for Continual Improvement |  | Scope : All the continual improvement projects identified by the MRM members & CFT team members. |  |  |  | Rev. Date : 01.02.2024
Department : Management Representative | [6 empty] | Page: 01 of 02
Step No. | Operation / Activity Description | Means/Device | When? | Record / Document | Responsibility | Reaction Plan | Photograph / Sketch, if applicable
1 | Identify the project for continual improvement through review of inspection report, non-conformities identified corrective action report, result of analysis of data, experience of the people in the organization. | Manually | At the start of CIP | Receiving Inspection Report ( STPPL / QA / FM / 28 & 47) Inprocess Inspection Report ( STPPL / QA / FM / 04 ) Corrective action report ( STPPL / QA / FM / 43) | MRM Members | - | -
2 | Decide the continual improvement project for implementation with due consideration of - a) Identification of the methodology used, objectives, effectiveness, and documented information; b) A manufacturing process improvement action plan with emphasis on the reduction of process variation and waste; c) Risk analysis (e.g., FMEA). | Manually | At the start of CIP | List of continual improvement project (STPPL/MR/LT/16) | Department Head | - | -
3 | Prepare continual improvement activity chart ( ensure that time requirement, technical needs, availability of technical know how or training need etc. & logical sequence of all the activities are considered | Manually | Each time of CIP | Quality Circle Team (STPPL / MR / CH / 02) Continual Improvement Activity Plan ( STPPL / MR/ FM / 05 ) | Department Head | - | -
4 | Prioritize the continual improvement plans depending on financial requirements, expected customer requirements, time requirements etc. | Manually | Each time of CIP | Continual Improvement activity chart ( STPPL / MR/ FM / 05 ) | Department Head | - | -
5 | Decide the responsibility & target date for each activity defined in the continual improvement activity chart. | Manually | Each time of CIP | Continual Improvement activity chart ( STPPL / MR/ FM / 05 ) | Department Head | - | -
6 | Review the status of continual improvement plans every month, or frequency decided in the continual improvement activity chart or during MRM decide for any changes required if any during the implementation. | Manually | Each time of CIP | Continual Improvement activity chart ( STPPL / MR/ FM / 05 ) | M.R. | - | -
7 | Review the effectiveness & efficiency of the continual improvement project after the completion of the project. | Manually | Each time of CIP | - | M.R. | - | -
8 | Review the possibility of changes in the QMS due to the CI project & fill document change note. | Manually | Each time of CIP | Document Change Request Note ( STPPL / MR / FM / 06 ) Document / Format Distribution & Control (STPPL / MR / FM / 16) | M.R. | - | -
9 | Approve the changes. | Manually | Each time of CIP | - | M.R. | - | -
10 | Update the approved changes in the relevant documents & distribute updated documents & formats to the concerns. | Manually | Each time of CIP | Document Change Request Note ( STPPL / MR / FM / 06 ) | M.R. | - | -
11 | Access the possibility of taking up similar improvement projects in other area | Manually | Each time of CIP | - | M.R. | - | -
12 | Display the achievement through CI projects & the names of the person involved. | Manually | Each time of CIP | - | M.R. | - | -
Review Date:- 01.02.2024 Review Due on:- 01.02.2025
Revision History :
Sr. No. | Revision in Document |  | Existing No. | Revised No. | Initiated by | Approved by | Prepared by :
1 | Continual Improvement, SOP no.changed. Old - 11 No. New - 7 No. |  | 0 / 01.06.2017 | 1 / 29.06.2018 | Vaibhav Pawar | R.U.Bhutekar
2 | Step No.03 Revised and added Quality Circle Team Chart in Record / Document colum. |  | 1 / 29.06.2018 | 2 / 06.07.2018 | Vaibhav Pawar | R.U.Bhutekar | Approved by :
3 | Step no. 02 revised for consideration during implementation of project. |  | 2 /06.07.2018 | 3 / 01.03.2018 | Vaibhav Pawar | R.U.Bhutekar
4 | Step no. 02 revised for list of continual improvement project. |  | 3 / 01.03.2018 | 04 / 23.07.2020 | Sonusingh Rathod | R.U.Bhutekar
5 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  | 04 / 23.07.2020 | 04 / 01.01.2022 | Sonusingh Rathod | R.U.Bhutekar
6 | Review date row added and logo changed |  | 04 / 01.01.2022 | 05 / 04.02.2023 | C. Khose | R.U.Bhutekar
7 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  | 05 / 04.02.2023 | 05 / 01.02.2024 | A. Deshmukh | R.U.Bhutekar