## Rev 03 (3)
STPPL | Standard Operating Procedure |  | Purpose : To standardise the process for Tool Development. |  |  |  | STPPL / MKD / SOP / 02
| Title : Tool Development. |  | Scope : New Tool Development. |  |  |  | Rev. No. :03
Department / Process Owner : Marketing and Development | [6 empty] | Rev. Date : 01.02.2025
Step No. | Operation / Activity Description | Means/Device | Frequency | Record / Document | Responsibility | Reaction Plan | Photograph / Sketch, if applicable
1 | Receive the Enquiry from customer in the form of Drawing / Sample. Log the enquiry in enquiry register. | Manual / Mail / Telephone / Courrier | Each time of enquiry | Enquiry Register (STPPL/MKD/FM/01) | Officer Marketing / Marketing Process Owner | Response time to new enquiry should be within two working days. | -
2 | Send the enquiry to tool maker. Use the enquiry form available with us and take the quotation. | Manual / Mail / Courrier | Each time of enquiry | Enquiry Form (STPPL/MKD/FM/04) | Project Leader / Development Engg. | - | -
3 | If project is feasible on the basis of commercial things and scope for development, send our quotation to Customer and then take confirmation from customer in the form of Purchase order, LOI or any written communication. | Manual / Mail / Courrier | Each time of enquiry | Enquiry Register STPPL / MKD / FM / 01 Preliminary / Initial Feasibility Study (STPPL/MKD/FM/23) Quotation (STPPL/MKD/FM/08) P.O in Customer Format, LOI, Written communication. | Officer Marketing / Marketing Process Owner | If not feasibile , inform to customer. In case customer does not specify exact requirement, CR will coordinate with customer for the same. | -
4 | Form the CFT for APQP and take team feasibility comittment by technical and other required studies.Risk analysis to be done at the time of feasibility. | Manual | After receiving conformation from customer in the form of P.O, LOI or any written communication. | Team Feasibility Commitment (STPPL/MKD/FM/02) | Project Leader / Development Engg. & Project Team Members | - | -
5 | Prepare the P.O. annexure on the basis of points discussed in the meeting and regular requirement. | Manual | At the time of tool development | Team Feasibility Commitment (STPPL/MKD/FM/02) Anexure to P.O. for Tool Making (STPPL/MKD/FM/09) | Project Leader / Development Engg. | - | -
6 | Mention all the details about mould function, mould material and other in annexure. | Manual | At the time of tool development | Anexure to P.O. for Tool Making (STPPL/MKD/FM/09) | Project Leader / Development Engg. | - | -
7 | Prepare the P.O. and attach the annexure to P.O. and take sign of all concern persons present in the meeting. | Manual | At the time of tool development | Purchase Order (STPPL/PUR/FM/02) Anexure to P.O. for Tool Making (STPPL/MKD/FM/09) | Purchase Process Owner & Project Leader / Development Engg. | - | -
8 | Send the P.O. to tool maker along with Annexure to P.O. for Tool Making. Collect the acknowledgement copy for the same. | Manual / Mail / Courrier | At the time of tool development | Purchase Order (STPPL/PUR/FM/02) Anexure to P.O. for Tool Making (STPPL/MKD/FM/09) Supplier Acknowledgement | Project Leader / Development Engg. | - | -
9 | Prepare the payment note for the advance note against the P.O. | Manual / Mail / Courrier & SAP | At the time of tool development | Payment Advice (SAP Document) | Project Leader / Development Engg. | - | -
10 | Take the time plan from the tool maker for mould development. | Manual / Mail / Courrier | At the time of tool development | Mould Development Time Plan (STPPL/MKD/FM/22) | Project Leader / Development Engg. | - | -
11 | Monitor & update Mould Development Time Plan on weekly basis. Collect activity completion evidences from supplier as per decided time plan including Jig Fixture development. | Manual / Mail / Courrier | Weekly basis, At the time of tool development | APQP Time -Plan chart (STPPL/MKD/FM/03) Mould Development Time Plan (STPPL/MKD/FM/22) | Project Leader / Development Engg. | If any activity not completed as per decided time plan, then take actions plan & target date from suppliers for delays. | -
12 | As per Mould Development Time Plan, demand for the design of the mould and receive the mould design. | Manual / Mail / Courrier | At the time of tool development | APQP Time -Plan chart (STPPL/MKD/FM/03) Mould Development Time Plan (STPPL/MKD/FM/22) 3D CAD Data | Project Leader / Development Engg. | - | -
13 | Discuss the mould design received from tool maker and cross check the same as per our requirement. | Manual / Mail / Courrier & CAD Software | At the time of tool development | Tool Design Review Check Sheet (STPPL/MKD/FM/17) 3D CAD Data | Project Leader & Project Team Members | Inform Tool maker if there is any problem in the mould design and get the mould design corrceted. | -
14 | Discuss the mould design received from tool maker with customer also if required (in case of customer approval). | Manual / Mail / Courrier & CAD Software | At the time of tool development | Tool Design Review Check Sheet (STPPL/MKD/FM/17) 3D CAD Data | Project Leader / Development Engg. | - | -
15 | Communicate with tool maker for T0 and plan the trial as per date given by tool maker. | Manual / Mail / Courrier | At the time of tool development | Mould Development Time Plan (STPPL/MKD/FM/22) APQP Time Plan Chart (STPPL/MKD/FM/03) | Project Leader / Development Engg. | - | -
16 | Inspect the mould as per Mould Inspection Check Sheet before conduct the trial. | Manual | After tool development & before trial | Mould Inspection Check Sheet (STPPL/MKD/FM/13) | Project Leader / Development Engg. | - | -
17 | Conduct the Trial T0. | Manual | After tool development & after mould inspection | Trial Requisition Note (STPPL/MKD/FM/06) Trial Report (STPPL/MKD/FM/16) | Project Leader / Development Engg. | - | -
18 | Make SIR for T0 samples. | Manual | After T0 trial | Sample Inspection Report (STPPL/QA/FM/11) | Project Leader / Development Engg. | - | -
19 | Convey to tool maker about the corrections in the mould for mould functioning and dimensional correction, if required | Manual / Mail / Courrier / Telephone | After T0 trial | Trial Report (STPPL/MKD/FM/16) Sample Inspection Report (STPPL/QA/FM/11) | Project Leader / Development Engg. | - | -
20 | Get the corrections done in the mould from tool maker. | Manual | At the time of tool development | Trial Report (STPPL/MKD/FM/16) Sample Inspection Report (STPPL/QA/FM/11) | Project Leader / Development Engg. | - | -
21 | After the required number of trials & corrections get the mould approved. | Manual, Mail | At the time of tool development | Customer SIR / Customer written communication. | Project Leader / Development Engg. | Communicate with CR & ask for any written approval. | -
Review Date:- 01.02.2025 Review Due on:- 01.02.2026
Revision History :
Sr. | Revision in Document |  | Existing No. | Revised No. | Initiated by | Approved by | Prepared by :
1 | Logo Added |  | 0 | 1 / 23.01.2017 | J.B.Ramdasi | R.U.Bhutekar
2 | Added Step No.- 01,10,11,16 Edited Step No.- 02,03,04,05,09,10,11,12,15,17,18,19 & 21. Also review & revised all steps - Means /device, Frequency, Record /Documents, Responsibility & reaction plan etc.column. |  | 1 | 2 / 11.03.2019 | Vaibhav Pawar | R.U.Bhutekar | Approved by :
3 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  | 2 / 11.03.2019 | 02 / 01.01.2022 | Sonusingh Rathod | R.U.Bhutekar
4 | Review date row added and logo changed |  | 02 / 01.01.2022 | 03/ 04.02.2023 | C.khose | R.U.Bhutekar
5 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  | 03/ 04.02.2023 | 03/ 01.02.2024 | A. Deshmukh | R.U.Bhutekar
6 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  | 03/ 01.02.2024 | 03/ 01.02.2025 | A. Deshmukh | R.U.Bhutekar