## Rev 0 (2)
STPPL | Standard Operating Procedure |  | Purpose : To standardise the Procedure for Industrial product design |  |  |  | STPPL /MKD/ SOP / 20
| Title : Industrial Product Design |  | Scope : This SOP defines the structured process for designing and developing industrial products covering research, concept development, 3D modeling, prototyping. |  |  |  | Rev. No. : 0
Rev. Date : 01.02.2025
Department / Process Owner : Industrial Product Design | [6 empty] | Page 01 of 01
Step No. | Operation / Activity Description | Means/Device | Frequency | Record/Document | Responsibility | Reaction Plan | Photograph / Sketch, if applicable
1 | Conduct research to understand the problem, user needs, and market gaps. Define key challenges, constraints, and objectives. | Manual / Mail/ Phone | One Time | Presentation | Industrial Designer | - | -
2 | Conduct Initial Feasibility Analysis | Manual | One time | Feasibility analysis document | Industrial Designer | - | -
3 | List design requirements. | Manual | One time | Feasibility analysis document | Industrial Designer | -
4 | Generate multiple design concepts through brainstorming sessions. | Manual | As & when change required | Presentation | Industrial Designer | - | -
5 | Share concepts with client to review | Manual/Mail | As & when change required | Presentation | Industrial Designer | -
6 | Assess concepts against design specifications, requirements, and feasibility. Finalize the best concept for further development. | Manual | one time | Concept comparison matrix | Industrial Designer | - | -
7 | Detail out final concept | Manual | As & when change required | Presentation | Industrial Designer | - | -
8 | Create detailed 3D models using CAD software (Solidworks) | Manual | As & when change required | Solidworks STEP file | Industrial Designer/ 3D developer | - | -
9 | Develop physical prototypes using prototyping methods. Test prototypes for functionality, usability, and necessary design refinements. | Manual | As & when change required | prototype reviewed against design requiremnets document | Industrial Designer | - | -
10 | Make required changes in 3D | Manual | As & when change required | Solidworks STEP file | Industrial Designer | - | -
11 | Hand over to NPD team | Manual | One time | Handover document |  | - | -
Review Date:- 01.02.2025 Review Due on:- 01.02.2026
Revision History :
Sr. | Revision in Document |  |  | Existing No. | Revised No. | Initiated by | Approved by
1 | New SOP prepared |  |  | 0 / 15.05.2024 | ---- | Ms. Sarika Deshpande | Mrs. Ketaki Kokil
2 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  |  | 0 / 15.05.2024 | 0 / 01.02.2025 | Abhijit Deshmukh | Mrs. Ketaki Kokil