## Rev 05 (3)
STPPL | Standard Operating Procedure | Purpose : To standardise the procedure for Control Plan. |  |  |  |  | STPPL/MKD/SOP/ 13
| Title : Control Plan. | Scope : Development of New Product. |  |  |  |  | Rev. No.: 05
Department / Process Owner : Marketing & development. | [6 empty] | Rev. Date: 01.02.2025
Step No. | Operation / Activity Description | Means / Device | Frequency | Record / Document | Responsibility | Reaction Plan | Photograph / Sketch, if applicable
1 | Select the type of Control Plan : 1) Prototype: A description of the dimensional measurements, material and performance tests occurring during Prototype build.It is valid till Pre-Launch stage. 2) Pre-Launch: A description of the dimensional measurements, material and performance tests that will occur after Prototype and before normal Production.It is valid till pilot lot submission stage. 3) Production: A comprehensive documentation of product and process characteristics, process controls,tests, and measurement occurring during normal production. | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
2 | Control Plan Number : Enter the control plan document number used for tracking, if applicable. For multiple control pages, enter page number (page___of___). | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
3 | Part Number & Latest Change Level : Enter the number of the system, subsystem or component being controlled. When applicable, enter the latest engineering change level and/or issue date from the drawing specification. | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
4 | Part Description : Enter the name and description of the product/process being controlled | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | -
5 | Supplier/Plant : Enter the name of the company and the appropriate division, plant or department preparing the Control Plan. | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
6 | Supplier Code: Enter any specific supplier or work center identification number necessary for tracking purposes. | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
7 | Key Contact & Phone Number : Enter the name and telephone number of the primary contact responsible for the control plan. | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
8 | Core Team : Enter the name(s) and telephone number(s) of the individual(s) responsible for preparing the Control Plan to the latest revision. It is recommended that all of the team members’ names, phone numbers,and locations be included. | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
9 | Supplier/Plant - Approval/Date, Engineering Approval Date, Quality Approval Date & Other/Additional Approvals : If required obtain approval from engineering authority approval, quality authority or any other additional authority | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
10 | Origination Date & Revision Date : Enter the date when the original Control Plan was created and date when plan was last updated. | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
11 | Part / Process Number : The item number, usually from the engineering specification. If multiple part numbers are used they should all be listed. | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
12 | Process Name / Operation Description : Where possible, all of the steps in the production of the system, subsystem, or component should be described. These steps can be identified from a process flow chart | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
13 | Machine, Device, Tools For Manufacturing : For each operation that is described, identify the processing equipment, e.g., machine, device, jig, or other tools for manufacturing, as appropriate. | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
14 | CHARACTERISTICS : The distinguishing feature, dimension or property of a process or product on which variable or attribute data can be collected. Use visual aids where applicable. | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
15 | Number : Enter a cross reference number from other applicable documents such as a Process Map or FMEA etc. | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
16 | Product : Product Characteristics are the features or properties of the part, component or assembly that are described on engineering drawings or other primary engineering information. The Control Plan Team should identify the Special Product Characteristics which are a compilation of important Product Characteristics from all sources. | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
17 | Process : Process Characteristics are the process variables (input variables) that have a cause and effect relationship with the identified Product Characteristic. A Process Characteristic can only be measured at the time it occurs.The team should identify Process Characteristics for which variation must be controlled to minimize product variation. | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
18 | Special Characteristic Classification : Where and when required apply any special characteristic designation. Example designations include "safety", "critical", "significant ", "major", etc | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
19 | By use of special charateristic matrix (STPPL/MKD/FM/18) having identify all SC/CC parameter, In which we convert customer symbols in our own symbols, details of conversions are specified. | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members
20 | METHODS : The systematic plan deploying procedures, instructions and tools to control the process. | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
21 | Product / Process / Specification Tolerance : Specifications and tolerance are obtained from various engineering specifications and documents. | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
22 | Evaluation / Measurement Technique : This column identifies the measurement system to be used. This could include gages, fixtures, tools, and/or test equipment required to measure the part, process or manufacturing equipment. | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
23 | Sample Size & Frequency : When sampling will be used, list the sample size and frequency of sampling. | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
24 | Control Method : This column contains a brief description of how the operation will be controlled. Include procedure numbers where applicable. The control method utilized should be based on knowledge and analysis of the process. The control method is determined by the type of process that exists. | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
25 | Reaction Plan : The reaction plan specifies the corrective actions necessary to avoid producing nonconforming products or operating out of control. The actions should normally be the responsibility of the people closest to the process, the operator or supervisor, and be clearly designated in the plan | Manual | Each time | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
26 | Control plan & related documents i.e.inspection standard,operation instruction (WI), Packing standard etc.to be revised in case of changes.Rev.details & Revision history to be maintained.Changes are revieved & approved by CFT. | Manual | Each time of changes | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
27 | Review of control plan in case of shipped nonconforming product to the customer, any change occurs affecting product, manufacturing process, measurement, logistics, supply sources, production volume changes, or risk analysis, customer complaint and implementation of associated corrective action, set frequency based on risk analysis and regular reviews once in a year. If required by the customer, obtain customer approval after review or revision of control plan. | Manual | Each time of changes | Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. / Q.A process owner & Project Team Members | - | -
Review Date:- 01.02.2025 Review Due on:- 01.02.2026
Revision History :
Sr. | Revision in Document |  | Existing No. | Revised No. | Initiated by | Approved by | Prepared by :
1 | Logo Added |  | 0 | 1 / 23.01.2017 | JBR | RUB
2 | Step No. 26 added for review of the control plan. |  | 1 | 2 / 01.03.2018 | Vaibhav Pawar | R.U.Bhutekar | Approved by :
3 | Review & revised all steps Responsibility column. |  | 2 / 01.03.2018 | 3 / 11.03.2019 | Vaibhav Pawar | R.U.Bhutekar
4 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  | 3 / 11.03.2019 | 03 / 01.01.2022 | Sonusingh Rathod | R.U.Bhutekar
5 | Step 19 added - |  | 03 / 01.01.2022 | 04 / 30.07.2022 | C. Khose | R.U.Bhutekar
6 | Review date row added and logo changed |  | 04 / 30.07.2022 | 05 / 04.02.2023 | C. Khose | R.U.Bhutekar
7 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  | 05 / 04.02.2023 | 05 / 01.02.2024 | A. Deshmukh | R.U.Bhutekar
8 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  | 05 / 01.02.2024 | 05 / 01.02.2025 | A. Deshmukh | R.U.Bhutekar