## Rev 10 (2)
STPPL | Standard Operating Procedure |  | Purpose : To standardise the Procedure for Control of design and engineering changes. |  |  |  | STPPL /MKD/ SOP / 08
| Title : Control of Design and Engg Changes. |  | Scope : For any change in product requirement ( including change at the sub supplier). Person authorized for change approval - MKD Head. |  |  |  | Rev. No. :10
Rev. Date : 01.02.2025
Department / Process Owner : Marketing & development | [6 empty] | Page 01 of 01
Step No. | Operation / Activity Description | Means/Device | Frequency | Record/Document | Responsibility | Reaction Plan | Photograph / Sketch, if applicable
1 | Get the information about the change required in the product/ Process. | Manual / Mail/ Phone | As & when change required | - | Officer Marketing / Marketing Process Owner / Process Owner | - | -
2 | Check the necessity to change the product/ process/RM. | Manual | As & when change required | - | Officer Marketing / Marketing Process Owner / Process Owner | - | -
3 | Study the process/ product /RM change affects. | Manual | As & when change required | Modification Review Check List (STPPL/MKD/FM/14) | Project Leader / Development Engg. & CFT Team | - | -
4 | Make the modification review for change in the product/process along with the concern department heads. During review the point of adverse impact on product due to change to be consider. | Manual | As & when change required | Modification Review Check List (STPPL/MKD/FM/14) | Project Leader / Development Engg. & CFT Team | - | -
5 | Consider all the check points in the modification review meeting and conclude the decision and sign the report. | Manual | As & when change required | Modification Review Check List (STPPL/MKD/FM/14) | Project Leader / Development Engg. & CFT Team | - | -
6 | Give the feedback to customer within ten working days about the feasibility of modification in case of change suggested by customer. | Mail/ Phone/Meeting face to face | As & when change required | Modification Review Check List (STPPL/MKD/FM/14) | Officer Marketing / Marketing Process Owner | Also communicate for any difficulty in the modification and get the report of same. | -
7 | Validate the change in product/ process | - | As & when change required | Validation report | Project Leader / Development Engg. & CFT Team | - | -
7 | Approve the change required in the process/ product/ RM. If appropriate & necessary obtain documented approval, or documented waiver, from the customer. To be intimated & get waiver approval in case of the deviation observed with reference to customer requirement. | Manual / Mail | As & when change required | Modification Review Check List (STPPL/MKD/FM/14) Deviation Request Form ( STPPL / QA / FM / 29 ) | Officer Marketing / Marketing Process Owner | --- | -
8 | Conduct necessary appropriate validation to be carried out prior to implementation change. | Manual | As & when change required | List of 4M Change (Planned & Unplanned) (STPPL/QA/LT/10) | Officer Marketing / Marketing Process Owner & CFT Team | And revised PPAP as required to be done as necessary. | -
9 | When ever there is change in RM or RM supplier from our side then material should be test for REACH or ROHS | Manual | As & when change required | List of 4M Change (Planned & Unplanned) (STPPL/QA/LT/10) | Officer Marketing / Marketing Process Owner & CFT Team | - | -
10 | Process of engineering change is applicable to the changes at the external providers also. If necessary a trial run to be planned and carry out at external provider. | Manual | As & when change required | Trial Requisition Note (STPPL/MKD/FM/06) Trial Report (STPPL/MKD/FM/16) | Purchase Head & Q.A Head | Revised PPAP as required to be done as necessary. | -
11 | Retention period for the records of REACH or ROHS should be as per customer specified specific requirements. | Manual | As & when change required | Customer specific requirements matrix (STPPL/QA/CH/03) | Officer Marketing / Marketing Process Owner & CFT Team | - | -
12 | Ensure relevant persons are made aware of the changed requirements, by way of written communication through E-mails, oral communication in DWM. Provision of necessary appropriate training to all concern people, if found applicable. | Manual / Mail | As & when required | - | Officer Marketing / Marketing Process Owner & CFT Team | Distribute the revised documented information (drawings, specifications, standards, PPAP, inspection plan etc.) to concerned and appropriate disposition of the old documented information. | -
Review Date:- 01.02.2024 Review Due on:- 01.02.2025
Revision History :
Sr. | Revison in Document |  | Existing No. | Revised No. | Initiated by | Approved by | Prepared by :
1 | Added enginnering change control for external provider. |  | 2 | 3 / 17.02.2018 | Vaihav Pawar | R.U.Bhutekar
2 | Added Sr. No. 08, for provison of ECN change validation. Sr. No 4 revised with adverse impact, Scope modified with authority.Sr. No. 06 modify for reply ECN within ten working days. |  | 3 / 17.02.2018 | 4 / 01.03.2018 | Vaihav Pawar | R.U.Bhutekar
3 | Modified Step No.- 06, 08. Also review & revised steps - Means /device, Frequency, Record /Documents & Responsibility etc.column. |  | 4 / 01.03.2018 | 5 / 11.03.2019 | Vaihav Pawar | R.U.Bhutekar | Approved by :
4 | Step no. 07 revised by adding customer approval in case of deviation from customer requirement. |  | 5 / 11.03.2019 | 06 / 04.01.2021 | Vandana M. | R.U.Bhutekar
5 | Step no. 10 revised by adding distribution & disposition of related documented information. |  | 06 / 04.01.2021 | 07 / 05.07.2021 | Ravi Ranjan | R.U.Bhutekar
6 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  | 07 / 05.07.2021 | 07 / 01.01.2022 | Sonusingh Rathod | R.U.Bhutekar
7 | In step no. 1,3,7 RM word added and in step no 10 training point described. |  | 07 / 01.01.2022 | 08 / 30.07.2022 | C. Khose | R.U.Bhutekar
8 | Review date row added and logo changed |  | 08 / 30.07.2022 | 09 / 04.02.2023 | Umesh Tongire | R.U.Bhutekar
9 | Document review no addidtion & deletion so rev no will be same |  | 09 / 04.02.2023 | 09 / 04.02.2023 | Abhijit Deshmukh | R.U.Bhutekar
10 | Sr. No. 9 added for When ever there is change in RM or RM supplier from our side then material should be test for REACH or ROHS. Sr. No. 11 added for Retention period for the records of REACH or ROHS should be as per customer specified specific requirements. |  | 09 / 04.02.2023 | 10 / 01.02.2024 | Umesh Tongire | R.U.Bhutekar
11 | Sr. No. 9 added for When ever there is change in RM or RM supplier from our side then material should be test for REACH or ROHS. Sr. No. 11 added for Retention period for the records of REACH or ROHS should be as per customer specified specific requirements. |  | 10 / 01.02.2024 | 10 / 01.02.2025 | Abhijit Deshmukh | R.U.Bhutekar