## Rev 02 (3)
STPPL | Standard Operating Procedure |  | Purpose : To standardise the process for Management of Product Safety. |  |  |  | STPPL/MKD/SOP/ 17
| Title : Management of Product Safety. |  | Scope : Applicable for all new product and processs development and changes if any. |  |  |  | Rev. No. : 02
Rev. Date:01.02.2025
Department / Process Owner : Marketing and Development. | [6 empty] | Page : 01 of 01
Step No. | Operation / Activity Description | Means/Device | Frequency | Record/Document | Responsibility | Reaction Plan | Photograph / Sketch, if applicable
1 | Identify the statutory and regulatory product safety requirement at the time of feasibility study of the new product development or the engineering changes being decided. | Manual | Each time of product development | Team Fesibility Study (STPPL/MKD/FM/02) | Project Leader / Development Engg. & Project Team Members | - | -
2 | Review the customer specific requirements and customer notification specially related to product safety. | Manual | Each time of product development | Team Fesibility Study (STPPL/MKD/FM/02) | Project Leader / Development Engg. & Project Team Members | - | -
3 | Identify the product characteristics related to product and process safety points. | Manual | Each time of product development | Special Characteristic Matrix (STPPL/MKD/FM/18) | Project Leader / Development Engg. & Project Team Members | - | -
4 | Identification the appropriate controls of safety related characteristics of product at the appropriate point of manufacture. | Manual | Each time of product development | PFMEA (STPPL/QA/FM/13) Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
5 | Special approval for design PFMEA from the customer. | Manual | Each time of product development | PFMEA (STPPL/QA/FM/13) | Project Leader / Development Engg. & Officer Marketing / Marketing Process Owner | - | -
6 | Appropriate necessary training to be identified and provided to the person involved in product and asscociated manufacturing process. | Mnaual | Each time of product development | Training Need Identification (STPPL / HRA / FM / 03) Training Record (STPPL / HRA / FM / 06) | HR Process Owner & Project Team Members | - | -
7 | If appropriate and possible, a physical demo to be organized on impact of the non- fullfilment of the safety related parameter to the people involved in product safety and related manufacturing process. | Mnaual | Each time of product development | Training Need Identification (STPPL / HRA / FM / 03) Training Record (STPPL / HRA / FM / 06) | Project Leader / Development Engg. / HR Process Owner & Project Team Members | - | -
8 | Preperation of FMEA and Control Plans and special approvals by the customer. Specially for safety parameters. | Manual | Each time of product development | PFMEA (STPPL/QA/FM/13) Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
9 | Initiation of measures as reaction plans and necessary appropriate actions in case of charcteristics which are either not statistically capable or unstable. | Manual | Each time of product development | PFMEA (STPPL/QA/FM/13) Control Plan (STPPL/QA/FM/15) | Project Leader / Development Engg. & Project Team Members | - | -
10 | Prior approaval on the changes in product or processes with evaluation of effects on product safety from process and product changes. | Manual | Each time of changes in product or processes | 4M Change List (STPPL / QA / LT / 10) 4M Change Monitoring Sheet (STPPL/QA/FM/52) | Officer Marketing / Marketing Process Owner | - | -
11 | Lesson learned to be recorded and refred as a reference for new product developments. | Manual | After product development | Lesson Learnt (STPPL/MKD/FM/20) Team Fesibility Study (STPPL/MKD/FM/02) | Project Leader / Development Engg. & Project Team Members | - | -
12 | External providers should also be trained on the safety related to product and processes. | Manual | As and when applicable | Training Record (STPPL / HRA / FM / 06) | Purchase Process Owner | - | -
Review Date:- 01.02.2025 Review Due on:- 01.02.2026
Revision History :
Sr. No. | Revison in Document |  | Existing No. | Revised No. | Initiated by | Approved by | Prepared by :
1 | Review & revised steps - Frequency, Record /Documents & Responsibility column. |  | 0 / 01.03.2018 | 1 / 11.03.2019 | Vaibhav Pawar | R.U.Bhutekar
2 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  | 1/ 11.03.2019 | 01 / 01.01.2022 | Sonusingh Rathod | R.U.Bhutekar | Approved by :
3 | Review date row added and logo changed |  | 01 / 01.01.2022 | 02 / 04.02.2023 | C. Khose | R.U.Bhutekar
4 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  | 02 / 04.02.2023 | 02 / 01.02.2024 | A. Deshmukh | R.U.Bhutekar
5 | Document reviewed and found ok (no change required), so revision no. remains same and review date changed. |  | 02 / 01.02.2024 | 02 / 01.02.2025 | A. Deshmukh | R.U.Bhutekar